## Read Me
Equator Resolution — Insurance Enterprise & AI Risk Register
Severity × likelihood, with owners, controls and review dates.
SCORING
Severity 1–5 (5 = severe: regulatory action, direct harm to a party, or health-data breach).
Likelihood 1–5 (5 = expected). Score = severity × likelihood.
Score ≥ 15 = Board-level. 9–14 = executive. ≤ 8 = managed at function level.
THE TWO RISKS THAT DEFINE THIS VERTICAL
IN-R-01 A retail policyholder routed into arbitration.
IN-R-02 An Ombudsman one-year window expiring during an Equator mediation.
Both are scored severity 5 and both have controls in code, not merely in policy.

## Risk Register
Insurance Enterprise & AI Risk Register
Score = severity × likelihood. Tier is computed. Law stated as at July 2026.
ID | Category | Risk | Sev | Lik | Score | Tier | Controls | Owner | Review | Status
IN-R-01 | Regulatory | A retail policyholder is routed into arbitration | 5 | 2 |  |  | DB CHECK constraint; API 409; AI route set; mandatory classification with second-officer review; UAT U-05 and U-36 are release gates | Head of Legal | Each release | Open
IN-R-02 | Party harm | An Ombudsman one-year window expires during an Equator mediation | 5 | 2 |  |  | Clock engine with generated expiries; 90/60/30-day alerts; blocking 60-day prompt task; closure block on unowned clocks; automatic Critical incident on unprompted expiry | Head of Operations | Monthly | Open
IN-R-03 | Data | Health-data breach or misuse | 5 | 2 |  |  | Segregated schema and key; assignment-scoped, time-boxed access; immutable access log reviewed monthly; exclusion from analytics and AI enforced by CI scan; vertical DPIA | DPO | Monthly | Open
IN-R-04 | Integrity | Repeat-player capture of a neutral by an insurer | 4 | 4 |  |  | 40% concentration cap as a DB constraint; rotation; cooling-off; consumer-side panel quota; quarterly publication of outcomes by insurer; no insurer-only selection | Head of Panel | Quarterly | Open
IN-R-05 | Regulatory | Equator is perceived as, or presents itself as, an official forum | 5 | 2 |  |  | Standing signposting script delivered verbatim and recorded; brand and marketing review; AI guardrail IN-G-07 with four adversarial cases; footer disclaimer on every page | Head of Legal | Quarterly | Open
IN-R-06 | Legal | A settlement purports to waive a non-waivable statutory right | 4 | 2 |  |  | DB CHECK constraints (no_statutory_waiver, no_future_discharge); template control; neutral training; QA sample | Head of Legal | Each release | Open
IN-R-07 | Party harm | A discharge voucher is signed under compulsion without reservation | 4 | 3 |  |  | Form F-I17 tick-box; DB constraint requiring a reserved balance on under_protest; case-manager script; QA sample of closed cases where the amount was disputed | Head of Operations | Monthly | Open
IN-R-08 | AI | The AI gives a merits opinion or a claim valuation | 4 | 3 |  |  | Guardrails IN-G-03 and IN-G-04 with eight adversarial cases; 403 refusal; architectural separation of classification from routing; degradation path to the deterministic questionnaire | Head of Technology | Each release | Open
IN-R-09 | Legal | A fraud allegation is mediated | 4 | 2 |  |  | Triage screen-out; DB constraint (no mediation route where fraud_alleged); neutral standing instruction; escalation to Head of Legal | Head of Legal | Monthly | Open
IN-R-10 | Commercial | Insurers decline to participate at scale | 3 | 4 |  |  | Lead with the batched settlement day, which has an explicit cost case; publish participation rates; protocol template with reciprocal undertakings | Head of BD | Monthly | Open
IN-R-11 | Commercial | The insurer relationship is bought at the cost of process integrity | 5 | 2 |  |  | Standing Board instruction: no commercial arrangement may relax the three controls; refusals recorded and reported to the Board; fee cannot be linked to the settlement amount (Rule 27) | CEO | Quarterly | Open
IN-R-12 | Regulatory | Regulatory change (internal ombudsman guidelines, DPDP phasing, 2025 Act commencement) | 3 | 5 |  |  | Six-monthly review with named owners; every affected document listed in the [verify] register; triage logic and signposting table designed to be reconfigured, not rewritten | Head of Legal | Six-monthly | Open
IN-R-13 | Operational | Insurer non-performance of a signed settlement | 3 | 3 |  |  | Escrow or milestone structure; acceleration clause; registration under s.27; performance verified before closure (F-I20) | Head of Operations | Monthly | Open
IN-R-14 | Operational | Claim file not produced by the insurer | 2 | 4 |  |  | 14-day tracking; non-production recorded on the file and disclosed to the neutral; protocol undertaking | Head of Operations | Monthly | Open
IN-R-15 | Financial | Retail volume without insurer subscriptions — the vertical does not reach break-even | 3 | 3 |  |  | Financial model states the dependency explicitly; decision gate at month 18 (two protocols signed, or re-scope to a credibility and referral asset) | CFO | Quarterly | Open
IN-R-16 | Panel | Insufficient consumer-side neutrals at launch | 3 | 3 |  |  | Consumer-side quota is a go-live blocker in the readiness checklist; recruitment through legal-aid and consumer organisations | Head of Panel | Monthly | Open
IN-R-17 | Data | Medical records retained beyond the retention class | 4 | 2 |  |  | erase_after set at ingestion; daily erasure job; closure requires confirmation; quarterly audit | DPO | Quarterly | Open
IN-R-18 | AI | Bilingual divergence — different routes or clocks in हिंदी | 3 | 2 |  |  | Parity suite of 20 cases; routes and clocks come from the deterministic engine, not the model, in both languages | Head of Technology | Each release | Open
IN-R-19 | Reputation | A published outcome dataset is read as evidence of bias | 3 | 3 |  |  | Publish methodology alongside figures; publish case mix and claim-size distribution; explain that settlement rate is not a proxy for merit | Head of Legal | Quarterly | Open
IN-R-20 | Third party | A broker or hospital channel partner is perceived to influence outcomes | 3 | 3 |  |  | No fee sharing on referrals; no referrer role in neutral selection; a broker whose own conduct is in issue participates only as a party | Head of BD | Quarterly | Open

## Heat Map
Severity × Likelihood Heat Map
Count of risks in each cell.
Severity \ Likelihood | 1 | 2 | 3 | 4 | 5
5
4
3
2
1

## Control Map
Risk to Control Mapping
Every risk maps to a numbered control in the compliance workbook.
Risk | Control ID | Control | Enforcement layer | Test
IN-R-01 | IN-C-03 | No arbitration route on a retail policy | Database CHECK + API 409 + AI route set | UAT U-05, U-36; constraint test
IN-R-02 | IN-C-02 | Clock table complete, owned and alerted | Database GENERATED + trigger + scheduler | UAT U-11, U-12, U-31; clock cases C-09 to C-12
IN-R-03 | IN-C-05 / IN-C-06 | Health data segregated and excluded | Separate schema and key; CI scan | UAT U-15 to U-17, U-34
IN-R-04 | IN-C-07 | Concentration cap, rotation, publication | Database CHECK + panel system | UAT U-21, U-22
IN-R-05 | IN-C-01 | Signposting delivered and recorded | Application + trigger + call sampling | UAT U-01, U-07; guardrail G-07
IN-R-06 | IN-C-04 | No waiver of a non-waivable right | Database CHECK | UAT U-24, U-25
IN-R-07 | IN-C-08 | Voucher basis recorded | Database CHECK | UAT U-27, U-28
IN-R-08 | IN-C-11 | AI guardrails | Architecture + harness in CI | Guardrail suite
IN-R-09 | IN-C-09 | Fraud screened out of mediation | Database CHECK + triage rule | Constraint test
IN-R-13 | IN-C-10 | Performance verified before closure | Application + escrow reconciliation | UAT U-33
IN-R-17 | IN-C-05 | Retention and erasure | Scheduled job + closure confirmation | UAT U-33
IN-R-19 | IN-C-12 | Outcome publication with methodology | Reporting pipeline | UAT U-34