## Read Me
Equator Resolution — Family Platform: Test & UAT Plan
Acceptance scripts mapped to every workflow state, with traceability and sign-off.
HOW TO USE
- 'UAT Scripts' holds one or more acceptance scripts per workflow state, in Given / When / Then form.
- Record PASS/FAIL per script; CRITICAL scripts (red) must pass before go-live.
- 'Traceability' links requirement -> workflow state -> API endpoint -> script, so nothing ships untested.
- Log defects in 'Defect Log'; severity 1 blocks release.
- 'Sign-off' records business, legal, DPO and security acceptance.
ENTRY CRITERIA
- Build deployed to UAT; test data seeded; AI eval harness passed; no open severity-1 defects.
EXIT CRITERIA
- 100% of critical scripts pass; >=95% of all scripts pass; zero open severity-1/2 defects; all sign-offs obtained.

## UAT Scripts
UAT Acceptance Scripts
Given / When / Then per workflow state. Red = critical (must pass before go-live).
ID | Workflow state | Scenario | Given | When | Then (expected result) | Endpoint / component | Severity | Result | Tester / date | Notes
UAT-01 | intake | Party can start a case and give DPDP consent | Given a new user on the portal | When they complete F-01 (identity + DPDP consent) and submit F-02 | Then a case is created with a case number, consent is recorded with the notice version, and an audit event is written | POST /cases | Critical
UAT-02 | intake | Consent withdrawal is honoured | Given a party who consented | When they withdraw consent | Then processing for that purpose stops, the withdrawal is timestamped, and the party is told what happens next | POST /parties/{id}/consent | Critical
UAT-03 | screening | Screening is per-party and confidential | Given both parties in a case | When party A completes screening | Then party B cannot see it, is not told it occurred, and no screening content appears in any shared view | POST /cases/{id}/screening | Critical
UAT-04 | screening | A safety flag blocks joint sessions | Given a screening outcome of 'not_suitable_safety' or a raised safety flag | When any user attempts to schedule a JOINT session | Then the API returns 409, the UI disables the option, and shuttle/safety options plus support signposting are offered | POST /cases/{id}/sessions | Critical
UAT-05 | screening | Support is signposted on a safety outcome | Given a safety flag | When the party views their portal | Then support and protection-order information is visible without the other party seeing anything | GET /cases/{id} | Critical
UAT-06 | triaged | Route triage produces a defensible recommendation | Given a completed intake | When triage runs | Then a route (mediation / court_referral / safety_pathway / not_suitable) is returned with a rationale and is recorded | POST /cases/{id}/triage | High
UAT-07 | notice_served | Notice to the other party is served and tracked | Given a registered case | When the case manager serves notice (F-03) | Then delivery is recorded with channel and timestamp, and a response deadline is set | POST /cases/{id} (notice) | High
UAT-08 | response | Non-participation is handled gracefully | Given no response within the deadline | When the deadline passes | Then a non-commencement report is generated and the applicant is told their other remedies are preserved | PATCH /cases/{id} | High
UAT-09 | mediator_appointed | Appointment requires conflict check and disclosure | Given a shortlisted mediator | When appointment is attempted without a signed disclosure | Then the system blocks activation until the conflict check passes and the disclosure is signed | POST /cases/{id}/appointment | Critical
UAT-10 | mediator_appointed | A party can challenge the mediator | Given an appointed mediator | When a party raises a challenge | Then it is recorded, decided by the Institution, and a replacement can be appointed without data loss | POST /cases/{id}/appointment/challenge | High
UAT-11 | in_session | Case room enforces per-party walls | Given a joint session | When party A opens the case room | Then only shared material and A's own documents are visible; B's private material is absent from the payload | GET /cases/{id} | Critical
UAT-12 | in_session | Caucus notes are sealed to the mediator | Given caucus notes exist | When either party (or any non-mediator role) requests them via API or UI | Then access is refused and the attempt is audit-logged | POST /sessions/{id}/caucus-notes | Critical
UAT-13 | in_session | Recording requires both parties' consent | Given a session | When recording is enabled with only one consent | Then recording is prevented; with both consents it proceeds and is disclosed on screen | POST /cases/{id}/sessions | Critical
UAT-14 | in_session | Child-inclusive mediation requires consent and a specialist | Given a case with children | When child-inclusive mediation is scheduled | Then consent is captured and a trained specialist is required before the session can proceed | POST /cases/{id}/sessions | High
UAT-15 | settlement | MSA assembles only agreed terms | Given agreed issues in the tracker | When the MSA is generated | Then it contains only the agreed terms, flags unresolved issues, and is watermarked DRAFT until signed | POST /cases/{id}/settlement | High
UAT-16 | settlement | e-Sign and e-Stamp complete the instrument | Given a final MSA | When both parties e-Sign and the document is e-stamped | Then the signed artefact hash is stored, the state schedule is recorded, and the document becomes immutable | POST /documents/{id}/esign, /estamp | Critical
UAT-17 | settlement | Registration under s.20 is available and recorded | Given a signed MSA | When registration is requested | Then submission is recorded and the s.27 enforceability flag is set | POST /settlements/{id}/register | High
UAT-18 | escrow | Escrow releases only on verified milestones | Given a funded escrow | When a release is attempted with an unmet milestone | Then it is refused; when the milestone is verified the tranche releases with a receipt and audit entry | POST /escrow/{id}/release | Critical
UAT-19 | escrow | Obligation tracker flags non-compliance | Given a recurring maintenance obligation | When a due date passes unpaid | Then the tracker marks it non-compliant and alerts the case manager | GET /settlements/{id}/obligations | High
UAT-20 | court_referral | Court referral links and reports correctly | Given a court-referred matter | When the referral is linked and the outcome recorded | Then the court case number, referring provision and report status are stored and retrievable | POST /cases/{id}/court-referral | High
UAT-21 | closed | Closure produces a complete, auditable record | Given a settled case | When closure is executed | Then a closure report is issued, retention timers start, and the audit chain verifies end-to-end | PATCH /cases/{id} | Critical
UAT-22 | withdrawn | Withdrawal preserves remedies and confidentiality | Given a party withdraws | When the case is closed as withdrawn | Then confidentiality survives, no admissions are exported, and the party is told their remedies are preserved | PATCH /cases/{id} | High
UAT-23 | cross-cutting | AI answers carry disclaimers and provenance | Given any AI answer | When it is returned | Then it includes the not-advice line, citations resolving to real corpus chunks, and a human-handoff offer | POST /ai/explore | Critical
UAT-24 | cross-cutting | AI safety trigger escalates to a human | Given a disclosure of violence or self-harm | When the AI responds | Then support is surfaced, procedural content stops, and a human escalation is raised | POST /ai/explore | Critical
UAT-25 | cross-cutting | Audit chain is tamper-evident | Given a sequence of case actions | When an audit row is altered directly in the database | Then chain verification fails and the discrepancy is reported | (audit verification job) | Critical
UAT-26 | cross-cutting | Retention purge runs to policy | Given records past their retention period | When the purge job runs | Then those records are removed or anonymised per retention_policy and the action is logged | (retention job) | Critical
UAT-27 | cross-cutting | Accessibility and language | Given a party using the vernacular UI and a screen reader | When they complete intake | Then all flows are operable, labelled, and content is available in the selected language | (UI) | High
UAT-28 | cross-cutting | Role-based access is enforced | Given each role (party, mediator, case manager, admin) | When they attempt actions outside their scope | Then access is denied and logged; no data leaks in the API payload | (all endpoints) | Critical

## Traceability
Traceability — workflow state to script
Every workflow state must have at least one acceptance script.
Workflow state | Scripts | Count | Covered?
intake | UAT-01, UAT-02 | 2 | Yes
screening | UAT-03, UAT-04, UAT-05 | 3 | Yes
triaged | UAT-06 | 1 | Yes
notice_served | UAT-07 | 1 | Yes
response | UAT-08 | 1 | Yes
mediator_appointed | UAT-09, UAT-10 | 2 | Yes
in_session | UAT-11, UAT-12, UAT-13, UAT-14 | 4 | Yes
settlement | UAT-15, UAT-16, UAT-17 | 3 | Yes
escrow | UAT-18, UAT-19 | 2 | Yes
court_referral | UAT-20 | 1 | Yes
closed | UAT-21 | 1 | Yes
withdrawn | UAT-22 | 1 | Yes
cross-cutting | UAT-23, UAT-24, UAT-25, UAT-26, UAT-27, UAT-28 | 6 | Yes

## Defect Log
Defect Log
Severity 1 blocks release; severity 2 blocks unless formally accepted.
ID | Script | Description | Severity (1-4) | Status | Owner | Raised | Resolved

## Sign-off
Go-live Sign-off
All rows must be signed before the platform touches a real party.
Role | Scope of acceptance | Name & signature | Date
Business owner | Scope and outcomes accepted
Legal counsel | Statutory references, forms and enforceability accepted
Data Protection Officer | DPDP consent, minimisation, retention and breach controls accepted
Security | Access control, encryption, audit integrity and pen-test findings accepted
Safeguarding lead | Screening, safety flag and support pathways accepted
Head of Mediation | Panel, disclosure, confidentiality and process accepted
Engineering lead | Build complete; defects closed; monitoring in place
Exit criteria
Critical scripts passed
Critical scripts total
Critical FAILs (must be 0)
GO-LIVE DECISION