EQUATOR RESOLUTION

Institutional Family Mediation — Court Interface

Court-Referral MoU & Pilot Plan

Template memorandum with a Family Court, and the plan to evaluate a first pilot

Family & Marital Dispute Resolution vertical

July 2026  ·  Draft for legal sign-off  ·  www.equatorresolution.com

Draft for counsel and the court This is a starting point for discussion with a court. Any arrangement must comply with the Family Courts Act, 1984, section 89 CPC, the Mediation Act, 2023, and the directions of the court and the relevant High Court. Nothing here binds any court.

Part 1 — Memorandum of Understanding (template)

Parties and purpose

This Memorandum records the understanding between the [Family Court / District Judiciary / DLSA], [place] ("the Court") and Equator Resolution ("the Institution") for the referral of suitable family matters to institutional mediation, and the return of the outcome to the Court.

Heads of terms

| Clause | Substance |
| --- | --- |
| 1. Scope | Categories of matter the Court may refer — mutual-consent divorce, maintenance, custody and parenting, matrimonial property — and those excluded. |
| 2. Referral mechanism | Form of the referral order; transmission of the case particulars; the Institution's acknowledgement timeline. |
| 3. Screening | The Institution conducts confidential safety and suitability screening before any joint session and may report a matter as unsuitable without attributing fault. |
| 4. Panel | Mediators are drawn from the Institution's panel, certified and conflict-checked; the Court may indicate a preference (including gender). |
| 5. Timelines | Target period for completion and the process for seeking an extension from the Court. |
| 6. Confidentiality | The mediation is confidential (Mediation Act, s.22); the report to the Court is confined to settlement or non-settlement and the agreed terms. |
| 7. Reporting | Form and timing of the report; transmission of the signed settlement for the Court's consideration. |
| 8. Fees | Court-referred matters at concessional or nil cost to the parties as agreed; no fee negotiated directly with a party. |
| 9. Data protection | Roles under the DPDP Act, 2023; security; retention; no use of case data for AI training. |
| 10. Records & audit | Case register, anonymised statistics, and access for the Court's oversight. |
| 11. Training & liaison | Orientation for court staff; a named liaison on each side; periodic review meetings. |
| 12. Term, review & termination | Pilot term, review points, and termination without prejudice to pending matters. |
| 13. No delegation of judicial function | Nothing in this MoU delegates any judicial function; the Court alone decides the matter. |

For the Court: ____________________   For Equator Resolution: ____________________   Date: __________

Part 2 — Pilot plan

Objective

To test, with one or two Family Courts, whether institutional mediation administered by Equator produces faster, safer and more durable outcomes in suitable family matters than the current path — and to gather the evidence needed to decide whether to scale.

Scope & design

| Parameter | Pilot design |
| --- | --- |
| Sites | 1–2 Family Courts (one metro, one non-metro if possible) |
| Duration | 6 months of referrals, plus 6 months' follow-up for durability |
| Volume | Target 80–120 referred matters across sites |
| Matter types | Mutual-consent divorce; maintenance; custody & parenting; matrimonial property |
| Exclusions | Matters the Court considers unsuitable; those where screening indicates risk that cannot be safeguarded |
| Comparison | Baseline drawn from comparable matters in the preceding period at the same court |
| Cost to parties | Nil or concessional; funded by the Institution for the pilot |

Success criteria

| Measure | Target | How measured |
| --- | --- | --- |
| Settlement rate (full or partial) | ≥ 45% | Case records |
| Median time from referral to outcome | ≤ 60 days | Case records vs baseline |
| Durability at 6 months | ≥ 85% of settlements holding | Follow-up contact / compliance tracker |
| Party-reported fairness | ≥ 4.0 / 5 | Anonymous exit survey, both parties |
| Party-reported safety | No party reports feeling unsafe or pressured | Exit survey + screening records |
| Child-focus quality | Parenting plan in ≥ 90% of child matters | Document audit |
| Court satisfaction | Positive; willingness to continue | Structured interview with judges and staff |
| Cost per matter | Within modelled unit economics | Finance records |

Governance & evaluation

A joint steering group (court liaison, Institution lead, an independent evaluator) meets monthly.

Independent evaluation — an academic or civil-society partner reviews the data and writes the report; the Institution does not mark its own homework.

Ethics — informed consent for data use; anonymised reporting; no case identifiers published.

Stop conditions — the pilot pauses immediately if a safety incident occurs, if settlement quality is poor, or if the Court asks.

Risks and mitigations

| Risk | Mitigation |
| --- | --- |
| Referral volume too low | Court orientation; simple referral form; regular liaison |
| Unsuitable matters referred | Clear scope; screening; a no-fault route to return a matter |
| Safety incident | Screening as condition precedent; safety flag; immediate escalation and pause |
| Settlements that do not hold | Quality drafting; independent-advice prompts; compliance tracking |
| Perception of privatising justice | Nil cost to parties; transparent reporting; the Court decides everything |

Outputs

A published evaluation report; a refined referral protocol; a costed proposal for scaling; and the evidence base for the annual *State of Family Mediation in India* report.