## Read Me
Equator Resolution — Enterprise & AI Risk Register (Family)
Inherent and residual risk, treatment, owner and review — including AI model risk.
HOW TO USE
- Score Likelihood (1-5) x Impact (1-5). Inherent = before controls; Residual = after controls.
- Rating bands: 1-4 Low · 5-9 Medium · 10-14 High · 15-25 Critical (auto-coloured).
- Every CRITICAL or HIGH residual risk needs a named owner, a treatment and a review date.
- 'AI Risk' covers model-specific risk; 'Red Team' is the adversarial testing plan.
- Review quarterly and on any material change, incident or new feature.

## Enterprise Risks
Enterprise Risk Register
Inherent score before controls; residual after. Review quarterly.
ID | Category | Risk | Cause | Consequence | Inh. L | Inh. I | Inh. score | Existing controls | Res. L | Res. I | Res. score | Further treatment | Owner | Review date | Status
R-01 | Safety | A party is harmed after mediation proceeded despite abuse indicators | Screening missed or overridden; pressure to settle | Serious harm; liability; catastrophic reputational damage | 4 | 5 | 20 | Screening as condition precedent; safety flag blocks joint sessions at API level; DV-trained mediators; escalation protocol | 2 | 5 | 10 | Mandatory screening audit; quarterly safeguarding review; incident drill | Safeguarding lead
R-02 | Safety | A child is harmed or used as leverage | Poor child-focus practice; coercive parent | Harm to child; regulatory and reputational consequences | 3 | 5 | 15 | Welfare-first training; child-inclusive specialist certification; no child-as-messenger rule; escalation to authorities | 2 | 5 | 10 | Case audit of all child matters; specialist sign-off | Head of Mediation
R-03 | Confidentiality | Caucus or screening content leaks to the other party | Design flaw; role misconfiguration; human error | Breach of s.22; loss of trust; possible claim | 3 | 5 | 15 | Sealed encrypted storage; no cross-party read endpoint; RBAC; access logging; UAT-12 test | 1 | 5 | 5 | Annual penetration test on access controls | CTO
R-04 | Data protection | Personal-data breach (DPDP) | Cyber attack; processor failure; insider | Board penalty; notification duties; harm to parties | 3 | 5 | 15 | Encryption; MFA; least privilege; DPAs with processors; breach runbook; retention limits | 2 | 4 | 8 | Tabletop breach exercise twice yearly; DPIA refresh | DPO
R-05 | Legal | A settlement is set aside or held unenforceable | Poor drafting; capacity or coercion; statutory non-compliance | Loss of core value proposition; claims | 3 | 4 | 12 | Standard MSA templates; counsel review; independent-advice prompts; capacity checks; e-stamp & s.20 registration | 2 | 4 | 8 | Quarterly sample review of MSAs by counsel | General Counsel
R-06 | Regulatory | Institution not recognised / non-compliant once MCI rules are notified | Rules differ from assumptions; delay in application | Inability to operate as an MSP; rework | 3 | 4 | 12 | Track MCI developments; design to the Act; readiness checklist; counsel watching brief | 2 | 3 | 6 | Quarterly regulatory horizon scan | General Counsel
R-07 | Regulatory | Unauthorised practice of law / holding out as advice | Staff or AI overstepping; marketing language | Regulatory action; professional complaints | 3 | 4 | 12 | No-advice policy; scripted boundaries; AI guardrails G1/G2; marketing review | 2 | 3 | 6 | Annual training; marketing sign-off by counsel | General Counsel
R-08 | Operational | Mediator misconduct or partiality | Inadequate vetting; no supervision | Harm to party; panel credibility | 2 | 4 | 8 | Empanelment vetting; Code of Conduct; disclosure; complaints process; suspension powers | 2 | 3 | 6 | Annual re-scoring; peer review | Head of Mediation
R-09 | Operational | Escrow funds mishandled or delayed | Bank error; instruction ambiguity; fraud | Financial loss; loss of trust | 2 | 5 | 10 | Regulated escrow agent; dual control; milestone verification; reconciliation; audit log | 1 | 4 | 4 | Monthly reconciliation; annual escrow audit | CFO
R-10 | Operational | Platform outage during live mediations | Infrastructure failure; dependency outage | Disrupted sessions; missed statutory clocks | 3 | 3 | 9 | Multi-AZ; monitoring; incident response; fallback to phone/in-person; RPO 1h/RTO 4h | 2 | 3 | 6 | Quarterly DR test | CTO
R-11 | Financial | Volumes below plan; runway pressure | Slow adoption; court referrals delayed | Insolvency risk; forced cuts | 4 | 4 | 16 | Staged hiring tied to volume; pilot-led growth; concession funding ring-fenced; scenario model | 3 | 3 | 9 | Monthly cash review; trigger points for cost action | CFO
R-12 | Financial | Fee model deters access / concessions unfunded | Pricing wrong; demand for waivers | Access-to-justice failure; reputational criticism | 3 | 3 | 9 | Published concessions; pro-bono allocation; means test; funded from commercial verticals | 2 | 2 | 4 | Semi-annual pricing review | CFO
R-13 | Reputational | Perception of privatising family justice | Misunderstanding of role; poor case outcome publicity | Loss of court and public confidence | 3 | 4 | 12 | Court decides everything; transparent reporting; nil-cost pilots; independent evaluation | 2 | 3 | 6 | Annual transparency report | CEO
R-14 | People | Key-person dependency (senior mediators, engineering) | Small team; specialist skills | Delivery failure; quality drop | 3 | 3 | 9 | Documented runbooks; cross-training; panel depth; succession notes | 2 | 2 | 4 | Quarterly capability review | COO
R-15 | Vendor | Critical processor failure (e-Sign, e-Stamp, video, cloud) | Vendor outage or exit | Service interruption; contractual exposure | 3 | 3 | 9 | DPAs; SLAs; exit plans; alternate providers identified; data portability | 2 | 3 | 6 | Annual vendor review | COO
R-16 | Compliance | Records or retention non-compliance | Purge job failure; unclear policy | Regulatory exposure; evidentiary gaps | 2 | 3 | 6 | retention_policy table; automated purge; audit; documented legal basis | 1 | 3 | 3 | Semi-annual retention audit | DPO

## AI Risk
AI Model Risk Register
Model-specific risk. Every row maps to guardrails and eval cases.
ID | Risk theme | Risk | Cause | L | I | Score | Controls | Guardrails | Assurance | Owner | Status
AI-01 | Harmful advice | Model gives legal advice or predicts an outcome a party relies on | Prompt drift; model update; user pressure | 4 | 5 | 20 | System prompt boundaries; output classifier; eval suite ADV-01..03; not-advice line | G1,G2 | Eval gate + weekly transcript sample
AI-02 | Missed safety signal | A disclosure of violence or self-harm is not detected | Oblique phrasing; language variation | 3 | 5 | 15 | Input pre-classifier; multilingual safety lexicon; conservative thresholds; eval suite SAF-01..04 | G3,G4,G5 | Recall measured each release; red-team quarterly
AI-03 | Hallucination | Model invents a provision, judgment or citation | Retrieval miss; parametric fallback | 4 | 4 | 16 | RAG-only answering; relevance floor; abstain path; citation validation; eval HAL-01..03 | G7 | Zero-tolerance gate on fabricated citations
AI-04 | Partiality | Output favours one party or coaches tactics | Prompt phrasing; user framing | 3 | 4 | 12 | Neutrality rules; refusal patterns; eval NEU-01..03 | G6,G10 | Bias review across gender/language/regime
AI-05 | Confidentiality leak via AI | Model surfaces the other party's material or caucus content | Retrieval scoping error | 2 | 5 | 10 | Per-case retrieval scoping; no cross-party index; eval CON-01..02 | G8 | Access-scope test each release
AI-06 | Prompt injection | Instructions hidden in an uploaded document change behaviour | Untrusted content in context | 3 | 4 | 12 | Content sanitisation; instruction isolation; eval INJ-01..02 | G11 | Red-team quarterly
AI-07 | Data misuse | Party data used for training or retained by a vendor | Weak contract; default vendor settings | 2 | 5 | 10 | Contractual no-training/no-retention; DPA; config review; DPIA | G12 | Annual vendor attestation
AI-08 | Model drift / regression | A model or prompt update degrades safety or accuracy | Vendor upgrade; prompt change | 4 | 4 | 16 | Version pinning; full eval harness before promotion; rollback plan | all | Release gate; regression threshold 2pt
AI-09 | Over-reliance by staff | Mediator or case manager accepts AI output uncritically | Time pressure; automation bias | 3 | 3 | 9 | DRAFT watermarking; mandatory human review; training on limits | G14 | Sample audit of AI-derived documents
AI-10 | Inequitable performance | Quality lower in a language or for a personal-law regime | Corpus imbalance; training data | 3 | 4 | 12 | Bilingual corpus; per-language eval; regime-balanced test cases | G6 | Annual equity review
AI-11 | Availability | AI service outage blocks intake | Vendor outage | 3 | 2 | 6 | Graceful degradation to human intake; feature kill switch | G13 | DR test
AI-12 | Explainability | Unable to explain why an answer was given | No provenance capture | 2 | 3 | 6 | Log retrieved doc ids, prompt & model version in ai_interaction | G7 | Reproducibility spot-check

## Red Team Plan
Red-Teaming & Assurance Plan
Adversarial testing outside the build team; findings become eval cases.
Cadence | Theme | Method | Owner | Linked risks
Quarterly | Safety bypass | Disclose abuse or self-harm obliquely, in Hindi and English, to test detection recall | Safeguarding + external tester | AI-02
Quarterly | Coercion | Attempt to have the AI draft threats or pressure a party into settling | External tester | AI-04
Quarterly | Confidentiality | Attempt to extract the other party's documents or caucus notes via the assistant and the API | Security | AI-05, R-03
Quarterly | Injection | Embed overriding instructions in uploaded PDFs and messages | Security | AI-06
Each release | Hallucination | Request non-existent authorities and provisions; check abstention | QA | AI-03
Each release | Advice boundary | Push for outcome predictions and recommendations | QA | AI-01
Annual | Equity | Compare answers across gender, language and personal-law regime | Counsel + QA | AI-10
Annual | Access control | Full role-based access and privilege-escalation test | External pen-tester | R-03, R-04

## Governance
Risk Governance
Who owns what, and how often it is looked at.
Forum | Cadence | Remit
Board | Quarterly | Approves risk appetite; reviews critical and high residual risks
Risk & Compliance Committee | Monthly | Owns the register; tracks treatment; escalates
Safeguarding Panel | Monthly + on incident | Reviews every safety incident and near-miss
AI Governance Forum | Monthly | Approves model/prompt releases; reviews eval results and incidents
DPO | Continuous | DPDP compliance, DPIA, breach response
Internal Audit | Annual | Independent assurance over controls