## Read Me
Equator Resolution — Consolidated [verify] & Legal Sign-off Register (all five verticals)
The single register counsel and the Board work from before go-live. Supersedes the per-vertical registers for tracking.
HOW TO USE
- '[verify] Register' lists every open legal/factual item across all five verticals, with an owner and a check date.
- 'Sign-off Matrix' tracks counsel/DPO/Board sign-off by document family and vertical.
- 'Statutes Relied On' is the consolidated authority list.
- Nothing goes live in any vertical until that vertical's blocking items are Cleared.
Law stated as at July 2026. Verticals: Family (Fam), Commercial (Com), Financial (Fin), Workplace (WP), Insurance (Ins).

## Verify Register
[verify] Register — all verticals
Every open legal/factual item, with an owner and a check date.
ID | Vertical | Category | Item to verify / clear | Owner | Check by | Note | Status
V-01 | Ins | Regulatory | Draft IRDAI (Internal Insurance Ombudsman) Guidelines, 2025 — finalisation & commencement | Head of Legal | On notification | Blocking for triage/signposting logic | Open
V-02 | Ins | Statute | Sabka Bima Sabki Raksha (Amendment of Insurance Laws) Act, 2025 — provisions actually brought into force | Head of Legal | Quarterly | Assent 20 Dec 2025; commencement to confirm | Open
V-03 | Ins | Regulatory | Insurance Ombudsman Rules — current monetary limits (Rs.50L/Rs.30L) & centre list | Head of Legal | Before go-live | Amended more than once | Open
V-04 | Ins | Case law | Pinpoint citations in the Compendium & Authorities Digest (SCC/INSC volume/page) | GC | Before external use | Case names verified; pinpoints to confirm | In progress
V-05 | Ins | Case law | Indian appellate authority on COVID business-interruption / virus exclusion | GC | Before citing | General doctrine only located; India-specific open | Open
V-06 | Ins | Regulatory | IRDAI PPHI 2024 / Master Circular exact clause refs for TAT & 2% interest | Head of Legal | Before quoting to a party | Timelines verified; clause refs to pin | In progress
V-07 | Ins | Scheme | PMFBY operational guidelines & PM-JAY grievance timelines — current version | Head of Ops | Before go-live | DGRC/SGRC & CGRMS ladders verified | In progress
V-08 | Ins | Regulatory | ULIP discontinuance charge caps & minimum interest (Form F-I21) | Head of Legal | Before go-live |  | Open
V-09 | Fam | Regulatory | Mediation Council of India operationalisation & mediation-service-provider recognition | GC | On notification | Recognition path designed to the Act; re-confirm | Open
V-10 | Fam | Statute | DPDP Act 2023 Rules — phasing & children's-data verifiable parental consent mechanics | DPO | On notification |  | Open
V-11 | Fam | Protocol | Mandatory-reporting pathway for child-at-risk / imminent harm — legal confirmation | GC | Before go-live | Blocking | Open
V-12 | WP | Statute | Labour Codes — State rules notification (uneven across States) | Head of Legal | Per State of operation | Codes in force 21 Nov 2025 | In progress
V-13 | WP | Statute | POSH Act s.10 (no monetary basis) & 90-day inquiry — confirm current position | GC | Before go-live | Verified; re-confirm at go-live | In progress
V-14 | WP | Statute | Code on Social Security 2020 — Employees' Compensation provisions notification | Head of Legal | On notification | Also affects Ins Employees' Comp routing | Open
V-15 | Fin | Regulatory | RBI Digital Lending Directions 2025 — final provisions | Head of Legal | Quarterly | Web-verified earlier; re-confirm | In progress
V-16 | Fin | Statute | NI Act s.143A/148 (interim compensation) & cheque-bounce pendency figures | GC | Before external use | Verified; refresh figures | In progress
V-17 | Fin | Statute | SARFAESI / DRT thresholds & RBI Integrated Ombudsman Scheme limits | Head of Legal | Before go-live |  | In progress
V-18 | Com | Statute | Commercial Courts Act s.12A 'specified value' threshold — current figure | GC | Before go-live | Drives the s.12A gate (C3) | Open
V-19 | Com | Statute | MSMED Act s.18 Facilitation Council process & interest — current position | Head of Legal | Before go-live | Drives C2 | In progress
V-20 | Com | Statute | A&C Act s.29A timetable & any amendment | GC | Quarterly | 12+6 months modelled | In progress
V-21 | All | Governance | Panel neutrals' professional indemnity — own cover vs group policy (Board decision) | COO | Before go-live | Live exposure flagged for decision | Open
V-22 | All | Data | Consolidated Platform DPIA approved by the Board (incl. health & POSH sub-stores) | DPO | Before go-live | See Platform DPIA pack | In progress
V-23 | All | Finance | Tariffs, financial models & market figures — Board approval and sourced data | CFO | Before go-live | Illustrative until approved | In progress
V-24 | All | Regulatory | Mediation Act 2023 s.27 registration workflow live with the prescribed authority | Head of Ops | Before go-live | Enforceability depends on it | In progress

## Sign-off Matrix
Sign-off Matrix — document family x vertical
Y = exists & in scope; Plat = platform-level; — = not applicable. Fill the Status column as counsel signs off.
Document family | Fam | Com | Fin | WP | Ins | Lead reviewer | Note
Master Blueprint | Y | Y | Y | Y | Y | GC
Rules of Mediation / Arbitration | Y | Y | Y | Y | Y | GC | Ins & Com carry arbitration limbs
Schedule of Fees / Tariff | Y | Y | Y | Y | Y | CFO | Board approval pending
Forms Pack | Y | Y | Y | Y | Y | GC
Public legal pages (ToS/Privacy/Grievance/Cookies) | Plat | Plat | Plat | Plat | Plat | GC/DPO | Platform-level
Practice guides / Compendium | Y | Y | Y | Y | Y | GC | Ins Compendium + Authorities Digest
Developer handoff / DDL / OpenAPI | Y | Y | Y | Y | Y | CTO | Com DDL+OpenAPI now added
Reference Implementation (runnable proof) | Y | — | — | Y | Y | CTO | Fam/WP shared; Ins now added; Com/Fin optional
AI eval harness / guardrails | Y | Y | Y | Y | Y | CTO | Now unified — see AI framework
Risk register | Y | Y | Y | Y | Y | COO
Institutional readiness pack | Y | Y | Y | Y | Y | COO | Fam now added
Training & certification curriculum | Y | Y | Y | Y | Y | Head of Panel | ECMN/ECCN/ECFC/ECWN/ECIN
Financial model | Y | Y | Y | Y | Y | CFO | Plus portfolio roll-up
DPIA / security | Plat | Plat | Plat | Plat | Plat | DPO | Consolidated platform pack

## Statutes Relied On
Consolidated Statutes & Instruments
The authority base across all five verticals.
Instrument | Verticals | Status
Mediation Act, 2023 (s.27 enforceability) | All | In force
Arbitration & Conciliation Act, 1996 (ss.12, 29A, 31, 34, 36) | Com, Ins | In force
DPDP Act, 2023 & Rules | All | In force; phased [verify]
Consumer Protection Act, 2019 | Ins, Fin | In force
Insurance Act, 1938 (s.45) | Ins | In force
Insurance Ombudsman Rules, 2017 (am. 2021) | Ins | In force [verify limits]
IRDAI circular 27 Oct 2023 (retail arbitration) | Ins | In force
IRDAI (PPHI) Regulations, 2024 + Master Circulars | Ins | In force
Sabka Bima Sabki Raksha (Amendment) Act, 2025 | Ins | Assent 20 Dec 2025 [verify commencement]
Motor Vehicles Act, 1988 (MACT) | Ins | In force
Employees' Compensation Act, 1923 / Code on Social Security, 2020 | Ins, WP | 1923 in force; Code phasing [verify]
Commercial Courts Act, 2015 (s.12A) | Com | In force [verify threshold]
MSMED Act, 2006 (s.18) | Com | In force
Companies Act, 2013 (oppression/mismanagement, NCLT) | Com | In force
Negotiable Instruments Act, 1881 (s.138, 143A, 148) | Fin | In force
SARFAESI Act, 2002 / RDB Act, 1993 (DRT) | Fin | In force
RBI Integrated Ombudsman Scheme, 2021 | Fin | In force
RBI Digital Lending Directions, 2025 | Fin | [verify final provisions]
Labour Codes (Wages/IR/OSH/Social Security) | WP | In force 21 Nov 2025; State rules [verify]
POSH Act, 2013 | WP | In force
Hindu Marriage Act 1955 / Special Marriage Act 1954 / personal laws | Fam | In force
Protection of Women from Domestic Violence Act, 2005 | Fam | In force
Guardians and Wards Act, 1890 / HMG Act, 1956 | Fam | In force
Mediation Act, 2023 — MCI recognition regime | All | [verify operationalisation]