EQUATOR RESOLUTION

An Infrabyx Group venture  ·  www.equatorresolution.com

UNIVERSITY & ACADEMIC PARTNERSHIP PROGRAMME

Programme Charter & Governance Framework

Mandate, scope, structure, roles, decision rights and reporting for the University & Academic Partnership Programme

| Document reference | EQ-UAP-014 |
| --- | --- |
| Document family | Governance |
| Version | v1.0 · Draft for legal sign-off |
| Date of issue | July 2026 |
| Law stated as at | 22 July 2026 |
| Owner | Director — Academic Partnerships, Equator ADR Institute |
| Approver | Managing Director, Equator Resolution |
| Classification | Confidential — Internal |

Not legal advice.  This document is a working draft prepared for Equator Resolution. Before it is used with any institution, student or party it must be reviewed by qualified counsel and, where personal data is involved, by the Data Protection Officer. Items marked [verify] must be cleared in the Master Legal Sign-off Register.

Document control

Version history

| Version | Date | Author | Summary of change | Status |
| --- | --- | --- | --- | --- |
| 0.1 | July 2026 | Equator ADR Institute | Initial drafting | Superseded |
| 1.0 | July 2026 | Equator ADR Institute | First complete issue for legal review | Draft for legal sign-off |

Review and approval

| Role | Name | Responsibility | Signature / date |
| --- | --- | --- | --- |
| Preparer | [●] | Drafting and factual accuracy |  |
| Reviewer — Legal | [●] | Statutory compliance; clause risk |  |
| Reviewer — Finance | [●] | Pricing, tax and revenue treatment |  |
| Data Protection Officer | [●] | DPDP Act 2023 and Rules 2025 compliance |  |
| Approver | [●] | Final approval for issue |  |

Distribution and related documents

| Item | Detail |
| --- | --- |
| Primary distribution | Managing Director; Director — Academic Partnerships; Legal; Finance |
| Counterparty distribution | Not for external release without approval |
| Related documents | See 00 — READ ME, University Partnership Programme |
| Retention | 7 years from expiry of the related MOU, unless a longer statutory period applies |
| Review cycle | Annual, or on any change of law affecting the subject matter |

Contents

This table of contents is a live field. Open in Word, select all (Ctrl+A) and press F9 to populate or refresh it.

…

# 1. Mandate

The University & Academic Partnership Programme is established by the Board of Equator Resolution to build and operate a national network of academic partnerships that delivers talent pipeline, institutional credibility and recurring revenue in support of the five dispute-resolution verticals.

The Programme is delivered principally through Equator ADR Institute, with Equator Resolution receiving referred matters, empanelling neutrals and employing programme graduates.

## 1.1 Objectives

| # | Objective | Measure | Owner |
| --- | --- | --- | --- |
| O1 | Build a tiered national network of partner institutions | Partnerships active by tier against plan | Director |
| O2 | Train students, faculty and professionals to a consistent standard | Participants certified; assessment pass rates; calibration variance | Head of Curriculum |
| O3 | Convert trained students into Equator interns, neutrals and employees | Conversion rate at each stage of the pipeline | Head of Operations |
| O4 | Generate recurring programme revenue at target contribution margin | Gross revenue; contribution margin; revenue per partnership | Finance Controller |
| O5 | Establish research and thought-leadership authority | Publications; annual report; citations; judicial and bar engagement | Head of Research |
| O6 | Operate without regulatory, safeguarding or reputational incident | Incidents; open [verify] items; audit findings | Director |

## 1.2 In scope

Partnership identification, contracting and governance; curriculum design and delivery; certification; competitions; internships; campus mediation cells; live clinics conducted under supervision; joint research; co-branded communications; institutional advisory services to partner institutions relating to grievance redressal, POSH and dispute resolution.

## 1.3 Out of scope

Award of degrees or diplomas; representation of any Equator credential as a statutory qualification; provision of legal advice to students or institutions; acceptance of a mediator or arbitrator appointment in a matter involving a partner institution save under the conflict protocol at 07.9; any activity outside India without separate Board approval.

# 2. Structure

## 2.1 Internal roles

| Role | Reports to | Principal accountabilities | Indicative FTE at steady state |
| --- | --- | --- | --- |
| Programme Director — Academic Partnerships | Managing Director | Strategy, tiering decisions, Tier 1 relationships, Board reporting, risk ownership | 1.0 |
| Manager — Business Development | Director | Pipeline, outreach, proposals, contracting hand-off, CRM discipline | 1.0 |
| Head of Curriculum & Certification | Director | Curriculum, trainer bench, assessment integrity, calibration, certification issue | 1.0 |
| Manager — Programme Operations | Director | Delivery calendar, logistics, vendor management, event execution | 1.0 |
| Competition Convenor | Head of Curriculum | Competition design, problem sets, rules, judges, integrity | 0.5, seasonal peak 1.0 |
| Coordinator — Internships & Clinics | Manager, Operations | Intern intake, supervision rota, clinic protocol, confidentiality compliance | 1.0 |
| Research Lead | Director | Research framework, joint publications, annual report, data governance | 0.5 |
| Marketing & Communications Executive | Director (dotted to Group Marketing) | Co-branded content, social media, press, ambassador programme | 0.5 |
| Finance Business Partner | Finance Controller | Pricing compliance, invoicing, revenue share, GST, collections | 0.3 |
| Legal Counsel (shared) | General Counsel | MOU and schedule review, clause bank maintenance, IP, regulatory watch | 0.3 |
| Data Protection Officer (shared) | Group DPO | DPDP compliance, consent architecture, breach response | 0.2 |
| Trainer bench (contracted) | Head of Curriculum | Delivery | 12+ certified trainers |

## 2.2 Governance bodies

| Body | Composition | Frequency | Decision rights |
| --- | --- | --- | --- |
| Programme Board | Managing Director (chair), Programme Director, Finance Controller, General Counsel | Quarterly | Strategy, annual plan, budget, tier assignments above threshold, exclusivity, exceptions to pricing policy |
| Programme Management Team | Programme Director (chair) and all internal role-holders | Fortnightly | Delivery calendar, resourcing, escalations, pipeline progression |
| Curriculum & Certification Committee | Head of Curriculum (chair), two senior trainers, one partner-institution academic, Research Lead | Quarterly | Curriculum changes, assessment standards, certification decisions, trainer certification |
| Competition Committee | Competition Convenor (chair), Head of Curriculum, two external practitioners, one host-institution representative | Per edition, minimum three meetings | Problem approval, rules, judge panel, integrity rulings, appeals |
| Joint Steering Committee (per partnership) | Two nominees from each party, chaired alternately | Semi-annual minimum | Partnership calendar, activity review, issue resolution, renewal recommendation |

The Joint Steering Committee has no authority to vary the MOU, to agree pricing outside the rate card, or to commit Equator resources beyond the agreed calendar. Its charter is at 10.1.

# 3. RACI

R = responsible, A = accountable, C = consulted, I = informed.

| Activity | Director | BD | Curriculum | Operations | Finance | Legal | DPO |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Institution scoring and tiering | A | R | C | I | I | I | — |
| Outreach and proposal | A | R | C | I | C | I | — |
| Pricing a proposal | A | C | I | I | R | I | — |
| MOU and schedule negotiation | A | R | C | C | C | R | C |
| Data protection clearance | I | I | I | C | I | C | A/R |
| Partnership activation | A | I | C | R | I | I | I |
| Curriculum design and change | I | I | A/R | C | I | C | — |
| Trainer certification and calibration | I | — | A/R | C | — | — | — |
| Programme delivery | I | I | C | A/R | I | — | — |
| Competition design and integrity | I | I | A | R | C | C | C |
| Internship intake and supervision | I | I | C | A/R | I | C | C |
| Live clinic authorisation | A | — | C | R | — | C | C |
| Invoicing and revenue share | I | I | — | C | A/R | C | — |
| Co-branded publication | A | C | C | I | I | C | I |
| Incident and escalation | A | I | I | R | I | C | C |
| Annual review and renewal | A | R | C | C | C | C | I |

# 4. Decision rights and escalation

## 4.1 Escalation ladder

| Level | Trigger | Resolver | Response time |
| --- | --- | --- | --- |
| L1 | Routine delivery issue — scheduling, logistics, materials | Manager, Programme Operations | 2 working days |
| L2 | Partner dissatisfaction; assessment dispute; minor deviation from the agreed calendar | Programme Director | 5 working days |
| L3 | Contractual dispute; pricing concession sought; competition integrity challenge; media enquiry | Programme Board | 10 working days |
| L4 | Safeguarding incident; data breach; regulatory contact; litigation threat | Managing Director and General Counsel, immediately; Board notified | Same day |

## 4.2 Matters reserved to the Programme Board

Any exclusivity commitment.

Any partnership with a term exceeding five years.

Any pricing below the floor in the rate card.

Any commitment of capital expenditure to a campus facility.

Entry into any partnership outside India.

Any variation to the Master MOU body text as distinct from its schedules.

Termination of a Tier 1 partnership.

# 5. Reporting

| Report | Prepared by | Audience | Frequency | Content |
| --- | --- | --- | --- | --- |
| Delivery dashboard | Operations | Programme Management Team | Fortnightly | Calendar status, attendance, issues, next-period readiness |
| Pipeline report | BD | Programme Management Team | Fortnightly | Stage-by-stage pipeline against capacity ceiling |
| Partnership scorecard | Director | Programme Board | Quarterly | Per-partnership activity, revenue, KPI status, renewal signal |
| Financial pack | Finance | Programme Board | Quarterly | Revenue by line, contribution margin, receivables, revenue-share settlements |
| Risk and incident report | Director | Programme Board | Quarterly, and immediately on L4 | Risk register movement, incidents, open [verify] items |
| Annual programme review | Director | Board of Equator Resolution | Annual | Full-year performance, renewals, strategy re-base |

# 6. Programme principles

The three-outcome test governs. Pipeline, credibility or revenue — or the activity does not happen.

Standardise, then customise for a fee. Bespoke delivery destroys the margin that funds the programme.

Document everything. An activity without attendance records, assessment data, feedback and photographs cannot be evidenced to the partner, to an accreditor, or to the Board.

Never trade neutrality for revenue. The conflict protocol is not negotiable.

Protect students first. Safeguarding and confidentiality obligations override commercial and reputational considerations without exception.

Let weak partnerships lapse. Renewal is earned on the scorecard.