EQUATOR RESOLUTION

An Infrabyx Group venture  ·  www.equatorresolution.com

UNIVERSITY & ACADEMIC PARTNERSHIP PROGRAMME

Revised Go-to-Market Sequencing & Lean Year 1 Plan

Why the original sequencing was backwards, what to sell first, and the single decision that moves the year 1 result by ₹16 lakh

| Document reference | EQ-UAP-101 |
| --- | --- |
| Document family | Strategy |
| Version | v1.0 · Draft for legal sign-off |
| Date of issue | July 2026 |
| Law stated as at | 22 July 2026 |
| Owner | Director — Academic Partnerships, Equator ADR Institute |
| Approver | Managing Director, Equator Resolution |
| Classification | Confidential — Internal (Strictly) |

Not legal advice.  This document is a working draft prepared for Equator Resolution. Before it is used with any institution, student or party it must be reviewed by qualified counsel and, where personal data is involved, by the Data Protection Officer. Items marked [verify] must be cleared in the Master Legal Sign-off Register.

Document control

Version history

| Version | Date | Author | Summary of change | Status |
| --- | --- | --- | --- | --- |
| 0.1 | July 2026 | Equator ADR Institute | Initial drafting | Superseded |
| 1.0 | July 2026 | Equator ADR Institute | First complete issue for legal review | Draft for legal sign-off |

Review and approval

| Role | Name | Responsibility | Signature / date |
| --- | --- | --- | --- |
| Preparer | [●] | Drafting and factual accuracy |  |
| Reviewer — Legal | [●] | Statutory compliance; clause risk |  |
| Reviewer — Finance | [●] | Pricing, tax and revenue treatment |  |
| Data Protection Officer | [●] | DPDP Act 2023 and Rules 2025 compliance |  |
| Approver | [●] | Final approval for issue |  |

Distribution and related documents

| Item | Detail |
| --- | --- |
| Primary distribution | Managing Director; Director — Academic Partnerships; Legal; Finance |
| Counterparty distribution | Not for external release without approval |
| Related documents | See 00 — READ ME, University Partnership Programme |
| Retention | 7 years from expiry of the related MOU, unless a longer statutory period applies |
| Review cycle | Annual, or on any change of law affecting the subject matter |

Contents

This table of contents is a live field. Open in Word, select all (Ctrl+A) and press F9 to populate or refresh it.

…

# 1. Why this document exists

The strategy at 01.1 and the economics at 04.2 were built together, and when the numbers were finished they contradicted the plan. This document reconciles them. It supersedes section 6 of 01.1 (Sequencing) and section 8 of 04.2 (Portfolio view). Everything else in those documents stands.

Three findings drove the revision:

The lines the plan led with are the worst lines in the model. Student certificate courses earn 29.8% at a full cohort, turn negative below 33 students, and require a local trainer bench that does not exist. Curriculum licensing earns 88%, coaching 58% and advisory retainers 32% — none of which needs a bench, a campus or a cohort.

The trainer bench is the binding constraint on everything. Until a city has four certified trainers, student delivery in that city is uneconomic. Building the bench takes six to nine months and was not planned for.

The year 1 loss is almost entirely a hiring decision. Running the programme on an existing executive's time in year 1 rather than a dedicated hire changes the result from a ₹25.8 lakh loss to a ₹9.3 lakh loss.

# 2. The revised principle

Sell what needs no infrastructure first. Build infrastructure with the proceeds. Then sell what needs it.

| Sequence | Sell | Because |
| --- | --- | --- |
| Phase 1, months 1–12 | Advisory retainers · coaching · faculty development · institutional workshops · curriculum licensing | High margin; deliverable by two or three senior people; no bench, no cohort, no campus dependency |
| Phase 2, months 13–24 | Add student certificate courses in bench cities only · membership tier · first own competition | The bench now exists where it is needed; the brand has evidence behind it |
| Phase 3, months 25–36 | Scale student delivery nationally · licence curriculum to third parties · residential schools | Infrastructure is in place and the offering is proven |

## 2.1 What this changes in practice

| Original plan | Revised plan |
| --- | --- |
| Sign two Tier 1 anchors first | Sign institutional advisory clients first — they need no MOU, no tier, no calendar |
| Run a 40-hour student cohort in month 3 | Run the first FDP in month 3; student cohorts wait for the bench |
| Launch the national competition in year 1 | Sponsor and judge at three existing competitions in year 1; launch our own in year 2 |
| Hire a full programme team from month 1 | Two people plus fractional support in year 1; build the team against revenue |
| Target the leading NLUs | Target the tier below, where the ground is not already occupied (see 01.7) |
| Build the bench "before scaling" | Build the bench in one named city as a funded year 1 objective (see 07.11) |

# 3. The hiring decision

This is the largest single variable in the year 1 result and it deserves to be decided consciously.

|  | Scenario A — Founder-led | Scenario B — Full team |
| --- | --- | --- |
| Programme Director | An existing Equator executive at 50% allocation | Dedicated hire from month 1 |
| Manager — BD and Programmes | 1.0 FTE hire | 1.0 FTE hire |
| Coordinator | 0.4 FTE | 1.0 FTE |
| Curriculum, Operations, Research | Not yet; contracted in | Hired |
| Fixed cost, year 1 | ₹36.9 lakh | ₹53.4 lakh |
| Contribution, year 1 | ₹27.6 lakh | ₹27.6 lakh |
| Year 1 result | (₹9.3 lakh) | (₹25.8 lakh) |
| Capacity to deliver | Adequate for the Phase 1 mix | Under-utilised |
| Risk | Director's attention is split | Cash burn before evidence exists |

Recommendation: Scenario A. The Phase 1 mix — advisory, coaching, FDP — is senior-heavy and volume-light, which is exactly what a part-time senior person plus one full-time manager can deliver. Hiring a dedicated Director in month 1 buys capacity the year 1 revenue mix cannot use.

The trigger for moving to Scenario B is contracted forward revenue of ₹1 crore, which on the plan below occurs in month 13 to 15.

# 4. Year 1 revenue plan — Phase 1 mix

| # | Line | Units | Unit revenue | Revenue | Contribution |
| --- | --- | --- | --- | --- | --- |
| 1 | Advisory retainer, comprehensive (ADV-A) | 3 | 3,60,000 | 10,80,000 | 3,42,000 |
| 2 | Advisory retainer, standard (ADV-B) | 3 | 1,80,000 | 5,40,000 | 1,56,000 |
| 3 | Coaching, international circuit | 5 | 2,25,000 | 11,25,000 | 6,50,000 |
| 4 | Coaching, national circuit | 3 | 1,10,000 | 3,30,000 | 1,47,000 |
| 5 | Faculty Development Programme | 6 | 3,50,000 | 21,00,000 | 7,31,400 |
| 6 | Institutional workshops, full day | 10 | 65,000 | 6,50,000 | 3,65,000 |
| 7 | POSH and grievance sessions | 3 | 90,000 | 2,70,000 | 1,35,000 |
| 8 | Curriculum licences | 2 | 1,25,000 | 2,50,000 | 2,20,000 |
|  | Total |  |  | 63,45,000 | 27,46,400 |
|  | Blended contribution margin |  |  |  | 43.3% |

Note the margin. At 43.3% it is materially above the 30% assumed in the original year 1 plan, for one reason: the mix contains no student certificate courses. That is the whole argument in a single number.

## 4.1 Year 1 cost base — Scenario A

| Line | Amount |
| --- | --- |
| Programme Director, 50% allocation of an existing executive | 12,00,000 |
| Manager — Business Development and Programmes | 12,00,000 |
| Coordinator, 0.4 FTE | 2,40,000 |
| Shared services — finance, legal, DPO allocation | 3,00,000 |
| Travel and business development | 4,00,000 |
| Marketing, collateral and digital | 2,50,000 |
| Competition sponsorship and judging at three existing events | 3,50,000 |
| Trainer bench build — certification of the first cohort (see 07.11) | 4,00,000 |
| Systems, insurance, contingency | 2,00,000 |
| Total fixed cost | 45,40,000 |
| Contribution | 27,46,400 |
| YEAR 1 RESULT | (17,93,600) |

Note. This includes ₹4 lakh to build the trainer bench, which the original plan did not fund at all. Excluding that investment the operating loss is ₹13.9 lakh; excluding both the bench and competition sponsorship, ₹10.4 lakh. All three presentations are legitimate; the Board should see the middle one, because the bench is an investment and the competition spend is customer acquisition.

# 5. Year 2 — where the model turns

| # | Line | Units | Revenue | Contribution |
| --- | --- | --- | --- | --- |
| 1 | Advisory retainers, blended | 18 | 48,60,000 | 15,40,000 |
| 2 | Coaching, international | 12 | 27,00,000 | 15,60,000 |
| 3 | Coaching, national | 8 | 8,80,000 | 3,92,000 |
| 4 | Faculty Development Programmes | 12 | 42,00,000 | 14,62,800 |
| 5 | Student certificate cohorts, bench cities only | 8 | 21,28,000 | 6,33,600 |
| 6 | Institutional workshops | 24 | 15,60,000 | 8,76,000 |
| 7 | POSH and grievance sessions | 10 | 9,00,000 | 4,50,000 |
| 8 | Curriculum and casebook licences | 6 | 7,50,000 | 6,60,000 |
| 9 | Institutional membership | 15 | 26,25,000 | 18,00,000 |
|  | Total |  | 2,06,03,000 | 93,74,400 |
|  | Less competition edition 1 outturn |  |  | (2,19,500) |
|  | Less fixed cost, full team |  |  | (72,00,000) |
|  | YEAR 2 RESULT |  |  | 19,54,900 |

Two things do the work in year 2. The membership tier (line 9) contributes ₹18 lakh on ₹26 lakh of revenue because it bundles items with near-zero marginal cost. Advisory retainers (line 1) contribute ₹15.4 lakh with no seasonality and negligible delivery infrastructure. Between them they are more than the entire year 2 profit.

# 6. Three-year comparison

|  | Original plan | Revised plan |
| --- | --- | --- |
| Year 1 revenue | 38,00,000 | 63,45,000 |
| Year 1 result | (28,32,000) | (17,93,600) |
| Year 2 revenue | 1,53,10,000 | 2,06,03,000 |
| Year 2 result | (2,88,000) | 19,54,900 |
| Year 3 revenue | 3,11,54,000 | 3,64,00,000 |
| Year 3 result | 38,15,000 | 62,40,000 |
| Cumulative three-year result | 6,95,000 | 63,01,300 |
| Peak cash requirement | ~₹31 lakh | ~₹19 lakh |

[verify — all figures are planning estimates and must be re-based after the first two quarters of actual delivery.]

# 7. The competition decision

The original plan launched the Equator National Mediation Championship in year 1. The revised plan does not, for three reasons.

Edition 1 loses ₹2.2 lakh and needs ₹8.5 lakh of contracted sponsorship from relationships Equator does not yet have.

The circuit is crowded and established. NLIU Bhopal, NALSAR, Jamia Millia Islamia and NMIMS Indore all run mediation competitions in the February–March window, several with law firm and publisher backing. A first edition entering that field competes for the same teams, judges and sponsors from a standing start.

Sponsoring and judging at existing competitions is a fraction of the cost and better intelligence. ₹3.5 lakh across three events buys visibility with forty institutions, puts Equator neutrals on panels alongside the bench and bar, and — the point most often missed — reveals who actually writes cheques for ADR competitions in India before Equator asks anyone for ₹12 lakh.

## 7.1 Year 1 competition plan

| Event | Window | Equator's role | Cost |
| --- | --- | --- | --- |
| Fox & Mandal–NALSAR Mediation Tournament | February | Judges; delegate presence | 60,000 |
| XIV International Mediation Tournament, CADR, NLIU Bhopal | March | Named round or award sponsor; judges | 1,50,000 |
| Jamia Millia Islamia National Mediation Competition | February | Judges; award sponsor | 75,000 |
| NMIMS Indore Inter-University Mediation Competition | 2026 cycle | Judges | 40,000 |
| INADR International Law School Mediation Tournament, DY Patil | November | Judges; observation for format learning | 25,000 |
| Total |  |  | 3,50,000 |

Objectives, in order: identify and build relationships with the five sponsors who fund this circuit; recruit six judges to Equator's panel; sell coaching to at least four participating institutions; and select the host campus for Equator's own edition in year 2.

[verify — confirm current edition dates and sponsorship availability with each organiser.]

# 8. The bench-city strategy

Student delivery is only economic where four or more certified trainers are locally available. The revised plan therefore treats trainer density as a geographic objective, not a national one.

| Year | Bench cities | Certified trainers | Student cohorts possible |
| --- | --- | --- | --- |
| 1 | 1 — [●], recommended [●] | 6 | 0, bench in training |
| 2 | 2 | 14 | 8 |
| 3 | 4 | 26 | 22 |

City selection criteria, in order: density of target institutions within 90 minutes' travel; availability of practising mediators willing to train; presence of a court-annexed mediation centre from which to recruit; Equator's own case volume in that city; and cost of living, which sets the trainer day rate.

Rule: no student certificate course is sold in a city with fewer than four certified trainers. Where an institution in a non-bench city wants student training, sell the institution-paid block model instead, which absorbs travel, or defer.

# 9. Revised twelve-month calendar

| Month | Objective | Milestone |
| --- | --- | --- |
| 1 | Foundations | Scenario A team in place; bench city selected; target longlist scored |
| 2 | Advisory launch | Advisory collateral complete; first 10 Registrar approaches |
| 3 | First revenue | First FDP delivered; first advisory retainer signed |
| 4 | Bench recruitment | 8 trainer candidates identified; train-the-trainer scheduled |
| 5 | Coaching season opens | 5 coaching engagements contracted for the Feb circuit |
| 6 | Bench build | First train-the-trainer cohort delivered; 6 trainers certified |
| 7 | Consolidation | 3 advisory retainers live; 3 FDPs delivered; membership tier designed |
| 8 | Circuit preparation | Competition sponsorships contracted; judges recruited |
| 9 | Evidence | First case study published; first partner satisfaction survey |
| 10 | Mediation Week | Mediation Week run at two partner campuses; first workshops at scale |
| 11 | Circuit | Judging and sponsorship at the national circuit begins |
| 12 | Review and gate | Board review; Scenario B hiring gate tested; year 2 plan approved |

# 10. What must be true for this plan to work

| # | Condition | Owner | If it fails |
| --- | --- | --- | --- |
| 1 | Six trainers certified in the bench city by month 6 | Head of Curriculum | Student courses slip to year 3; year 2 revenue falls ~₹21 lakh |
| 2 | Six advisory retainers signed by month 12 | Director | The most reliable revenue line is unproven; reconsider the whole advisory thesis |
| 3 | Eight coaching engagements contracted by month 5 | BD | Margin mix falls; year 1 loss widens to ~₹24 lakh |
| 4 | Simulation packs and workbook complete by month 2 | Head of Curriculum | Nothing is deliverable. This is the hard prerequisite |
| 5 | Pitch deck and advisory collateral complete by month 2 | Marketing | BD cannot start |
| 6 | Competition sponsorships secured for year 2 by month 12 | Director | Own competition slips to year 3 |
| 7 | Membership tier designed and priced by month 7 | Finance | Year 2 profit turns negative — this line is ₹18 lakh of it |

Condition 4 is the one to act on this week. Every other condition assumes a curriculum that is currently designed but not manufactured.