EQUATOR RESOLUTION

An Infrabyx Group venture  ·  www.equatorresolution.com

UNIVERSITY & ACADEMIC PARTNERSHIP PROGRAMME

Competition Operations Manual & Run Sheet

Twenty weeks of countdown, the day-by-day run sheet, room protocol, scoring flow and contingency plans

| Document reference | EQ-UAP-069 |
| --- | --- |
| Document family | Competitions |
| Version | v1.0 · Draft for legal sign-off |
| Date of issue | July 2026 |
| Law stated as at | 22 July 2026 |
| Owner | Director — Academic Partnerships, Equator ADR Institute |
| Approver | Managing Director, Equator Resolution |
| Classification | Confidential — Internal and host institution |

Not legal advice.  This document is a working draft prepared for Equator Resolution. Before it is used with any institution, student or party it must be reviewed by qualified counsel and, where personal data is involved, by the Data Protection Officer. Items marked [verify] must be cleared in the Master Legal Sign-off Register.

Document control

Version history

| Version | Date | Author | Summary of change | Status |
| --- | --- | --- | --- | --- |
| 0.1 | July 2026 | Equator ADR Institute | Initial drafting | Superseded |
| 1.0 | July 2026 | Equator ADR Institute | First complete issue for legal review | Draft for legal sign-off |

Review and approval

| Role | Name | Responsibility | Signature / date |
| --- | --- | --- | --- |
| Preparer | [●] | Drafting and factual accuracy |  |
| Reviewer — Legal | [●] | Statutory compliance; clause risk |  |
| Reviewer — Finance | [●] | Pricing, tax and revenue treatment |  |
| Data Protection Officer | [●] | DPDP Act 2023 and Rules 2025 compliance |  |
| Approver | [●] | Final approval for issue |  |

Distribution and related documents

| Item | Detail |
| --- | --- |
| Primary distribution | Managing Director; Director — Academic Partnerships; Legal; Finance |
| Counterparty distribution | Not for external release without approval |
| Related documents | See 00 — READ ME, University Partnership Programme |
| Retention | 7 years from expiry of the related MOU, unless a longer statutory period applies |
| Review cycle | Annual, or on any change of law affecting the subject matter |

Contents

This table of contents is a live field. Open in Word, select all (Ctrl+A) and press F9 to populate or refresh it.

…

# 1. Countdown

| Weeks out | Task | Owner |
| --- | --- | --- |
| 28 | Host campus selected; dates fixed against the academic calendar and the national circuit | Convenor |
| 28 | Problem author commissioned | Convenor |
| 24 | Budget approved under 04.4; Schedule C executed with the host | Director |
| 22 | Sponsorship approach begins | Director |
| 20 | Invitation issued to institutions; registration opens | Convenor |
| 18 | Problem first draft; internal read-through | Author |
| 16 | Judge and mediator recruitment begins | Convenor |
| 14 | Problem test run with volunteers | Convenor |
| 12 | Title sponsor confirmed in writing, or the Committee reviews viability | Director |
| 12 | Problem revised; Committee approval | Committee |
| 10 | Registration closes; eligibility verification | Registration Officer |
| 9 | Draw made and published; sides allocated | Convenor |
| 9 | General Information released to all teams | Convenor |
| 8 | Confidential Information released, side-specific | Convenor |
| 8 | Room allocation, layout plan and signage brief to the host | Operations |
| 6 | Judges and mediators confirmed; conflict declarations collected | Convenor |
| 6 | Volunteer recruitment and briefing schedule agreed with the host | Host |
| 4 | Materials printed; folders assembled and numbered | Operations |
| 4 | Accommodation and travel confirmed for judges and staff | Operations |
| 3 | Mediation Plan deadline for preliminary round 1 | Teams |
| 2 | Scoring system tested end to end with dummy data | Scoring Officer |
| 2 | Judge and mediator packs despatched | Convenor |
| 1 | Volunteer briefing; site walkthrough; room dressing plan confirmed | Operations |
| 1 | Contingency plans confirmed — power, connectivity, judge absence, team absence | Operations |
| 0 | Delivery | All |
| +1 | Scoresheets returned to teams; sponsor report; photographs distributed | Operations |
| +4 | Post-event financial reconciliation and Committee review | Finance, Committee |
| +52 | Problem published; casebook updated | Convenor |

# 2. Run sheet

## Day 0 — set-up

| Time | Activity | Owner |
| --- | --- | --- |
| 09:00 | Site handover from host; room inspection | Operations, Host |
| 10:00 | Room dressing; signage; branding | Operations |
| 12:00 | Registration desk set up; folders laid out | Registration |
| 14:00 | Scoring room established — access controlled, one door | Scoring Officer |
| 15:00 | Volunteer briefing; roles and boundaries | Operations |
| 17:00 | Judge and mediator calibration briefing | Convenor |
| 19:00 | Team registration desk opens; declarations collected | Registration |
| 20:00 | Final walkthrough; contingency check | Operations |

## Day 1 — preliminary rounds 1 and 2

| Time | Activity |
| --- | --- |
| 07:30 | Staff and volunteers in position |
| 08:00 | Registration; devices policy explained; declarations verified |
| 09:00 | Opening ceremony — 30 minutes maximum, and keep it to that |
| 09:30 | Judges and mediators to allotted rooms; supervisors brief teams |
| 09:45 | Preliminary Round 1 begins — 85 minutes plus 10 minutes feedback |
| 11:20 | Round 1 ends; scoresheets collected by supervisors |
| 11:30 | Scores entered and verified; teams released for break |
| 12:30 | Lunch |
| 13:30 | Mediation Plans for Round 2 verified as submitted |
| 14:00 | Preliminary Round 2 begins |
| 15:35 | Round 2 ends; scoresheets collected |
| 16:00 | Scores entered and verified |
| 16:30 | Masterclass or panel session while scoring is completed |
| 18:00 | Close of day 1 |

## Day 2 — preliminary round 3 and quarter-finals

| Time | Activity |
| --- | --- |
| 08:30 | Registration; Round 3 plans verified |
| 09:00 | Preliminary Round 3 begins |
| 10:35 | Round 3 ends; scoresheets collected |
| 11:00 | Scoring lock. Rankings computed; two-person verification; Convenor signs |
| 11:45 | Quarter-finalists announced; supplementary confidential information issued |
| 12:00 | Lunch |
| 13:15 | Quarter-finals |
| 15:00 | Semi-finalists announced |
| 15:30 | Semi-finals |
| 17:15 | Finalists announced |
| 17:30 | Judicial–academic roundtable or keynote |
| 19:00 | Close |

## Day 3 — final and valedictory

| Time | Activity |
| --- | --- |
| 09:30 | Finalists briefed; final materials issued |
| 10:00 | THE FINAL — open to all delegates, in the main hall |
| 11:30 | Final ends; judges deliberate on individual awards |
| 12:00 | Valedictory session — feedback from the final panel; awards; Spirit of Mediation Award last |
| 13:00 | Lunch and close |
| 14:00 | Judge debrief; Committee first review |
| 15:00 | Pack down; host handover |

# 3. Session room protocol

| Element | Standard |
| --- | --- |
| Layout | One table for six; four competitor chairs, one for the mediator; judges seated apart with a clear view of all four competitors; supervisor at the door |
| Signage | Room number, session number, "Session in progress — do not enter" |
| Devices | Collected or switched off and placed on the supervisor's table |
| Water, notepads, pens | Provided |
| Timer | Visible to the mediator and the supervisor; not to the competitors |
| Entry | No entry once the session begins, except the supervisor and, with the mediator's permission, a Committee member |
| Coaches | Not admitted, in any circumstance |
| Photography | Only by the accredited photographer, only in the first two minutes, only with consent verified |

## 3.1 Supervisor script

Before: Confirm both teams present and correctly identified. Confirm declarations signed. Collect or confirm devices off. Confirm mediator and judges present and free of conflict for this session. Announce: This session is 85 minutes. I will signal at 15 minutes and 5 minutes remaining. The session stops at 85 minutes. Judges will give 10 minutes of feedback afterwards. Please begin when the mediator invites you.

During: Time the session. Signal at 15 and 5. Stop at 85. Note any rule breach. Do not intervene otherwise.

After: Invite judges' feedback. Collect scoresheets, check that all boxes are completed, the three observations are recorded, the arithmetic is done, Won or Lost is indicated, and the sheet is signed. A sheet missing any of these is returned to the judge immediately. Deliver sheets to the scoring room personally; do not hand them to a volunteer.

# 4. Scoring flow

| Step | Control |
| --- | --- |
| 1. Supervisor collects sheets | Checks completeness before leaving the room |
| 2. Delivered by hand to the scoring room | No volunteer handling; no photographs |
| 3. Entered by the Scoring Officer | Single entry |
| 4. Verified by a second person against the physical sheet | Two-person rule |
| 5. Arithmetic re-checked by the system and by hand on any sheet within 3 points | — |
| 6. Discrepancy | Referred back to the judge; never corrected unilaterally |
| 7. Ranking computed | Wins, then points, then differential, then plan score |
| 8. Convenor signs the ranking before announcement | Mandatory |
| 9. Physical sheets sealed and retained | Returned to teams after the Championship |

Scoring room rules. One door, controlled access. No competitor, coach, volunteer or institutional representative admitted. No photographs. Devices in the room are Equator's only. Scores are not announced by anyone other than the Convenor.

# 5. Contingencies

| Contingency | Plan |
| --- | --- |
| Judge fails to arrive | Reserve judge list of four, briefed and calibrated. Where none is available, a single judge scores, and the same arrangement is applied to at least one session of every affected team so that the round is comparable |
| Mediator fails to arrive | Reserve mediator list of two, drawn from the Equator panel |
| Team fails to arrive | Opposing team scored on a walkover at the mean of its other sessions; the absent team forfeits. Where absence is for a documented emergency, the Committee decides |
| Team member ill | Substitution permitted from the registered four; where the team falls below two, the Committee decides |
| Room unavailable | Two reserve rooms held for the whole Championship |
| Power failure | Host confirms backup; sessions require no power; scoring reverts to the paper sheets, which are the record in any event |
| Connectivity failure | Scoring is paper-first by design; entry can be deferred |
| Materials leak | Convenor informed immediately; Committee convenes; options are a supplementary confidential release, a re-draw, or disqualification of the affected team |
| Integrity challenge | Per Rule 11; determined before the next round proceeds |
| Medical incident | Host first aid; nearest hospital identified and posted in every room; incident reported within 24 hours |
| Media enquiry | Only the Convenor or the Programme Director speaks; volunteers and judges refer enquiries |

# 6. Volunteer roles and boundaries

| Role | Number | Boundary |
| --- | --- | --- |
| Registration | 4 | No access to competition materials |
| Room runners | 1 per 2 rooms | Do not enter during a session; do not handle scoresheets |
| Hospitality | 4 | No access to the scoring room or judges' area |
| Wayfinding | 4 | — |
| Photography assistant | 1 | Consent verified before any image |
| Judges' liaison | 2 | Do not discuss sessions; do not carry scoresheets |

Every volunteer signs the undertaking at F-10 and is briefed on the boundaries. Scoresheets are handled only by supervisors and the scoring team.

# 7. What the host institution provides and what Equator provides

Per Schedule C to the Memorandum. In summary: the host provides rooms, power, audio-visual, housekeeping, security, first aid, volunteers, hostel accommodation and internal permissions; Equator provides the problem, materials, rules, judges, mediators, supervisors, scoring, certificates, trophies, prize money, branding and the post-event report.

# 8. Post-Championship

| Task | By | Owner |
| --- | --- | --- |
| Scoresheets returned to teams | +7 days | Scoring Officer |
| Certificates issued | +7 days | Operations |
| Photographs and video distributed | +14 days | Marketing |
| Sponsor post-event reports | +30 days | Director |
| Financial reconciliation | +30 days | Finance |
| Committee review — what to change | +30 days | Committee |
| Recruitment follow-up with finalists and award winners | +14 days | Internships Coordinator |
| Host institution thank-you letter (L-21) with the full record | +7 days | Director |
| Problem archived; publication scheduled for +12 months | +30 days | Convenor |

The recruitment follow-up is the point most often missed. Every finalist and award winner should receive a personal approach within fourteen days. They have just been observed under pressure for three days by people whose judgement Equator trusts; that is better information than any interview process produces.