EQUATOR RESOLUTION

An Infrabyx Group venture  ·  www.equatorresolution.com

UNIVERSITY & ACADEMIC PARTNERSHIP PROGRAMME

Partnership Onboarding & Activation SOP

The thirty days from signature to first activity — what must happen, in what order, and who owns it

| Document reference | EQ-UAP-073 |
| --- | --- |
| Document family | Operations |
| Version | v1.0 · Draft for legal sign-off |
| Date of issue | July 2026 |
| Law stated as at | 22 July 2026 |
| Owner | Director — Academic Partnerships, Equator ADR Institute |
| Approver | Managing Director, Equator Resolution |
| Classification | Confidential — Internal |

Not legal advice.  This document is a working draft prepared for Equator Resolution. Before it is used with any institution, student or party it must be reviewed by qualified counsel and, where personal data is involved, by the Data Protection Officer. Items marked [verify] must be cleared in the Master Legal Sign-off Register.

Document control

Version history

| Version | Date | Author | Summary of change | Status |
| --- | --- | --- | --- | --- |
| 0.1 | July 2026 | Equator ADR Institute | Initial drafting | Superseded |
| 1.0 | July 2026 | Equator ADR Institute | First complete issue for legal review | Draft for legal sign-off |

Review and approval

| Role | Name | Responsibility | Signature / date |
| --- | --- | --- | --- |
| Preparer | [●] | Drafting and factual accuracy |  |
| Reviewer — Legal | [●] | Statutory compliance; clause risk |  |
| Reviewer — Finance | [●] | Pricing, tax and revenue treatment |  |
| Data Protection Officer | [●] | DPDP Act 2023 and Rules 2025 compliance |  |
| Approver | [●] | Final approval for issue |  |

Distribution and related documents

| Item | Detail |
| --- | --- |
| Primary distribution | Managing Director; Director — Academic Partnerships; Legal; Finance |
| Counterparty distribution | Not for external release without approval |
| Related documents | See 00 — READ ME, University Partnership Programme |
| Retention | 7 years from expiry of the related MOU, unless a longer statutory period applies |
| Review cycle | Annual, or on any change of law affecting the subject matter |

Contents

This table of contents is a live field. Open in Word, select all (Ctrl+A) and press F9 to populate or refresh it.

…

# 1. Why activation is a controlled process

Most partnerships that fail do not fail at negotiation. They fail in the ninety days after signature, when nobody converts the document into a calendar. This SOP exists to make that impossible.

Rule: a partnership is not "live" until the first-year Activity Calendar is signed by both Nodal Officers. Until then it is a signed document, which is not the same thing.

# 2. The thirty-day activation plan

| Day | Step | Owner | Output | Blocker if missed |
| --- | --- | --- | --- | --- |
| 0 | MOU executed; counterpart scanned and filed | BD | Executed MOU on the partnership file | — |
| 1 | Partnership record created in the CRM; tier, term, schedules, minimum activity recorded | BD | Record | Everything |
| 2 | Confirmation letter L-07 issued | Director | Letter | — |
| 3 | Internal handover meeting: BD to Operations and Curriculum | BD | Handover note | Delivery planning |
| 5 | Nodal Officers confirmed in writing on both sides | Director | Written confirmation | Calendar |
| 7 | Renewal review diarised at Term minus 90 days; minimum activity review diarised annually | Operations | Calendar entries | Renewal |
| 10 | Joint kick-off meeting | Director | Minutes and action list | Calendar |
| 12 | Campus facilities walkthrough and safety check | Operations | Facilities note | Any on-campus activity |
| 14 | Brand assets exchanged; co-branding approval route confirmed in writing | Marketing | Asset pack | Any communication |
| 15 | Data protection contacts exchanged; Data Addendum confirmed executed if any data will be shared | DPO | Contact record | Any registration |
| 18 | Trainer bench checked against the proposed calendar; capacity confirmed | Curriculum | Capacity confirmation | Calendar |
| 21 | First-year Activity Calendar drafted | Operations | Draft calendar | — |
| 25 | Calendar agreed and signed by both Nodal Officers | Director | Signed calendar | Partnership is not live until this exists |
| 27 | Commercial set-up: institution registered in the finance system; billing contacts; purchase order requirement recorded | Finance | Finance record | Invoicing |
| 28 | Joint announcement approved and released | Marketing | Announcement | — |
| 30 | Activation complete; partnership moved to Active; scorecard opened | Director | Scorecard | — |

Escalation. If day 25 passes without a signed calendar, the Programme Director writes to the Nodal Officer. If day 45 passes, letter L-18 is issued. If day 60 passes, the partnership is recorded as Signed but not activated and reported to the Programme Board.

# 3. The kick-off meeting

Attendees. Both Nodal Officers; Equator Programme Director and Operations Manager; the institution's academic coordinator; anyone from the institution who will actually organise things — which is frequently not the person who signed.

Agenda, 60 minutes.

| Item | Minutes |
| --- | --- |
| What we agreed, in plain terms — the schedules attached and what they commit each side to | 10 |
| The institution's academic calendar: term dates, examinations, vacations, festivals | 10 |
| Draft first-year calendar, built live on a shared screen | 20 |
| Facilities: what is available, when, and how it is booked | 5 |
| Communications: who approves what, and how quickly | 5 |
| Commercials: who raises the purchase order, who pays, when | 5 |
| Actions with names and dates | 5 |

Discipline. Do not leave the meeting without provisional dates for the first three activities. A meeting that ends with "we will revert on dates" produces a partnership that does not start.

# 4. Building the first-year calendar

## 4.1 Sequencing principles

Start with something free and visible. The guest lecture within the first sixty days. It costs nothing, it introduces Equator to the student body, and it generates the enquiry list for the first paid cohort.

Work around examinations. Nothing is scheduled in the four weeks before or during an examination period. This is the most common cause of a collapsed cohort.

Do not schedule the first paid programme before the free one. The free session is the marketing for the paid one.

Fix the competition round early. It requires the longest lead time and the most institutional coordination.

Leave 20% headroom. Calendars that are 100% full fail on the first disruption.

## 4.2 Template first-year calendar

| Month | Activity | Charged | Prerequisite |
| --- | --- | --- | --- |
| 1 | Guest lecture and programme launch | No | Nothing |
| 2 | Campus Mediation Cell constitution and selection | No | Guest lecture |
| 3 | Certificate course cohort 1 | Yes | Enquiry list from the guest lecture; trainer bench confirmed |
| 4 | Mediation advocacy workshop | Yes | — |
| 5 | Intra-university selection round | No | Cell established |
| 6 | Faculty Development Programme | Yes | Faculty list; institutional budget approved |
| 7 | Mediation Week | Cost-shared | Event plan 45 days in advance |
| 8 | Judicial–academic roundtable | Cost-shared | DLSA invitation issued 60 days in advance |
| 9 | Internship intake | No | Certificate cohort completed |
| 10 | Competition round hosted | Cost-shared | Schedule C; venue confirmed 12 weeks in advance |
| 11 | Certificate course cohort 2 | Yes | — |
| 12 | Annual review and Steering Committee | No | Scorecard prepared |

# 5. Handover from BD to Operations

The handover note must contain, and Operations must not accept it without:

| # | Item |
| --- | --- |
| 1 | Executed MOU and every attached schedule |
| 2 | Tier, term, minimum activity number, renewal date |
| 3 | Commercial terms: rates agreed, any discount and its approval, revenue-share split, collecting party, purchase order requirement |
| 4 | Any deviation from standard form, and its approval reference |
| 5 | Named champion and what they personally want from the partnership |
| 6 | Signing authority and internal approval route, with typical duration |
| 7 | Facilities offered, and on what basis |
| 8 | The institution's academic calendar |
| 9 | Discovery record and proposal issued |
| 10 | Anything promised verbally that is not in the document — stated explicitly |

Item 10 is the one that causes trouble. It is asked for directly at handover.

# 6. Common activation failures

| Failure | Cause | Prevention |
| --- | --- | --- |
| No calendar 60 days after signature | No named champion, or the champion has moved on | Confirm the champion at kick-off; if they have gone, find a successor before proceeding |
| First cohort under-subscribed | Paid programme scheduled before the free session | Follow the sequencing rule |
| Cohort collapses at short notice | Scheduled near examinations | Obtain the academic calendar at kick-off and check it |
| Purchase order not raised, activity delayed | Requirement not identified | Ask at handover and again at kick-off |
| Trainers unavailable for agreed dates | Calendar agreed without checking the bench | Day 18 capacity check is mandatory before the calendar is signed |
| Announcement made before approval | Enthusiasm | Approval route confirmed in writing on day 14 |
| Nothing happens for six months | Nobody owned it | The activation plan has a named owner on every line |

# 7. Activation checklist

| # | Item | ☐ |
| --- | --- | --- |
| 1 | Executed MOU and schedules on file | ☐ |
| 2 | CRM record created with tier, term and minimum activity | ☐ |
| 3 | Renewal and annual review dates diarised | ☐ |
| 4 | Both Nodal Officers named in writing | ☐ |
| 5 | Kick-off meeting held and minuted | ☐ |
| 6 | Facilities walkthrough completed and recorded | ☐ |
| 7 | Brand assets exchanged; approval route confirmed | ☐ |
| 8 | Data protection contacts exchanged; Addendum executed if required | ☐ |
| 9 | Trainer capacity confirmed against the calendar | ☐ |
| 10 | First-year Activity Calendar signed by both Nodal Officers | ☐ |
| 11 | Finance set-up complete; purchase order requirement recorded | ☐ |
| 12 | Joint announcement released | ☐ |
| 13 | Scorecard opened | ☐ |
| 14 | Partnership status changed to Active | ☐ |