EQUATOR RESOLUTION

An Infrabyx Group venture  ·  www.equatorresolution.com

UNIVERSITY & ACADEMIC PARTNERSHIP PROGRAMME

Trainer Bench — Recruitment, Economics & Development Plan

Where trainers come from, why they would work for Equator, what the bench costs to build, and the city-by-city targets that gate student delivery

| Document reference | EQ-UAP-106 |
| --- | --- |
| Document family | Operations |
| Version | v1.0 · Draft for legal sign-off |
| Date of issue | July 2026 |
| Law stated as at | 22 July 2026 |
| Owner | Director — Academic Partnerships, Equator ADR Institute |
| Approver | Managing Director, Equator Resolution |
| Classification | Confidential — Internal (Strictly) |

Not legal advice.  This document is a working draft prepared for Equator Resolution. Before it is used with any institution, student or party it must be reviewed by qualified counsel and, where personal data is involved, by the Data Protection Officer. Items marked [verify] must be cleared in the Master Legal Sign-off Register.

Document control

Version history

| Version | Date | Author | Summary of change | Status |
| --- | --- | --- | --- | --- |
| 0.1 | July 2026 | Equator ADR Institute | Initial drafting | Superseded |
| 1.0 | July 2026 | Equator ADR Institute | First complete issue for legal review | Draft for legal sign-off |

Review and approval

| Role | Name | Responsibility | Signature / date |
| --- | --- | --- | --- |
| Preparer | [●] | Drafting and factual accuracy |  |
| Reviewer — Legal | [●] | Statutory compliance; clause risk |  |
| Reviewer — Finance | [●] | Pricing, tax and revenue treatment |  |
| Data Protection Officer | [●] | DPDP Act 2023 and Rules 2025 compliance |  |
| Approver | [●] | Final approval for issue |  |

Distribution and related documents

| Item | Detail |
| --- | --- |
| Primary distribution | Managing Director; Director — Academic Partnerships; Legal; Finance |
| Counterparty distribution | Not for external release without approval |
| Related documents | See 00 — READ ME, University Partnership Programme |
| Retention | 7 years from expiry of the related MOU, unless a longer statutory period applies |
| Review cycle | Annual, or on any change of law affecting the subject matter |

Contents

This table of contents is a live field. Open in Word, select all (Ctrl+A) and press F9 to populate or refresh it.

…

# 1. Why this document exists

Every other document in this programme assumes trainers. None of them said where the trainers come from.

The bench is the binding constraint on the entire programme. Student certificate delivery earns 29.8% with local trainers and 6.1% with outstation trainers. Faculty development, workshops and residential schools all require certified people. The competition needs assessors. Coaching needs practitioners. Nothing scales past two or three engagements a month without a bench, and a bench takes six to nine months to build.

Risk R16 in the register scores this at 16 — the highest operational risk in the programme. This document is the mitigation.

# 2. What a certified trainer is

| Requirement | Standard |
| --- | --- |
| Basic mediation training | 40 hours completed, with Equator or recognised as equivalent |
| Advanced training | 20 hours completed |
| Practice | Not fewer than 20 mediations conducted, evidenced |
| Train-the-trainer | T-TTT completed — 3 days, assessed |
| Observation | Observed co-delivering at least one full programme before leading |
| Currency | Annual observation; calibration before every assessed cohort; [●] CPD hours a year |
| Conduct | Code of Conduct signed; conflicts declared; background matters disclosed |

Three tiers of bench member

| Tier | Can do | Cannot do |
| --- | --- | --- |
| Associate | Co-facilitate; run drills; observe and score simulations under supervision | Lead a programme; assess |
| Lead | Lead any catalogue programme; assess simulations | Assess a cohort they taught, where numbers permit otherwise |
| Principal | All of the above; observe and certify other trainers; design curriculum; act as competition assessor | — |

# 3. Where trainers come from

Five sources, in order of yield.

## 3.1 Court-annexed mediation centres and legal services authorities — the largest pool

Mediators trained under the court-annexed regime already hold the 40-hour basic and, in many cases, the 20-hour advanced qualification and have logged supervised mediations. They are the only pool in India that already meets Equator's practice requirement at scale.

|  | Detail |
| --- | --- |
| Where | District and High Court mediation centres; State and District Legal Services Authorities; the Arbitration and Conciliation Centre, Bengaluru; the Delhi Dispute Resolution Society; equivalents in each target city |
| Approach | Through the centre's coordinator, with a written note explaining that Equator is recruiting for a training panel and that empanelment is non-exclusive |
| Attraction | Supplementary income; appointments from Equator's own caseload; professional development; profile |
| Constraint | Many are practising advocates with unpredictable court diaries. Assume 40% of those recruited will deliver fewer than four programme-days a year |
| Yield estimate | 6 to 10 approaches per certified trainer |

## 3.2 Faculty who have completed Equator's Faculty Development Programme

Every FDP produces two to four faculty capable of becoming Associate trainers. They are already teaching, already comfortable in a room, and the pedagogy half of the FDP is precisely the gap most practitioners have.

|  | Detail |
| --- | --- |
| Constraint | They need the practice requirement — 20 mediations — which most will not have. Route them through supervised practice with Equator |
| Timeline | 12 to 18 months from FDP to Lead |
| Strategic value | A faculty member who trains for Equator is also the partnership champion. This source solves two problems at once |

## 3.3 Equator's own panel of neutrals

Neutrals already empanelled under 03.7. They have the practice, they know Equator's method, and the conflict position is already managed.

Constraint: a neutral earning well from appointments will not take ₹15,000 a day to train. Recruit selectively — those building a practice, those who enjoy teaching, and those who want the profile.

## 3.4 Retired judicial officers

High credibility, particularly with institutions and with the bar. Excellent for marquee sessions, judicial roundtables and competition assessment.

Constraint: style. A retired judge accustomed to determining disputes frequently finds facilitative mediation counter-intuitive and evaluates when they should facilitate. T-TTT is mandatory and observation is non-negotiable for this group, however senior.

## 3.5 Graduates of Equator's own advanced programme

The long-term answer and the reason the programme exists. From year 3, participants who completed T-40, T-20, supervised practice and T-TTT become the self-sustaining bench.

| Year | Share of bench from own graduates |
| --- | --- |
| 1 | 0% |
| 2 | 5% |
| 3 | 20% |
| 5 | 50%+ |

# 4. Why a good trainer would work for Equator

This is the question the original plan did not answer, and a day rate alone does not answer it.

## 4.1 What the day rate actually delivers

| Engagement level | Programme-days a year | Fee income |
| --- | --- | --- |
| Occasional | 6 | ₹90,000 |
| Regular | 16 | ₹2,40,000 |
| Committed | 30 | ₹4,50,000 |

For a practising mediator whose case income is lumpy and seasonal, ₹2.4 to ₹4.5 lakh of predictable supplementary income is meaningful. It is not, on its own, enough to secure the best people.

## 4.2 The bundle that does

| Element | Value to the trainer | Cost to Equator |
| --- | --- | --- |
| Appointments as neutral from Equator's caseload across five verticals | Fee-earning; case flow; the thing most mediators actually want | Nil — the work exists anyway |
| Panel listing with profile on Equator's public panel | Visibility to parties and referrers | Nil |
| Competition assessor role, national profile | Prestige; network with bench and bar | Honorarium only |
| Co-authorship on research drawing on Equator's caseload | Publication, which practitioners struggle to obtain | Nil |
| Adjunct or visiting association with a partner university | Academic standing; a title | Nil — arranged through the MOU |
| CPD, calibration and observation | Genuine development, free | Marginal |
| Referral flow from institutions and alumni | Practice building | Nil |
| Being part of a bench rather than working alone | Peer group; cover when unavailable | Nil |

The proposition to state in the recruitment conversation: We are not primarily offering you training work. We are offering you a place on a panel that will appoint you in real matters, a national competition to assess at, research to publish, an academic association, and training days that pay properly. The training is how you become known to us.

## 4.3 What loses trainers

| Cause | Prevention |
| --- | --- |
| Long gaps between engagements | Minimum-engagement understanding; if fewer than four days a year, say so honestly at recruitment |
| Late payment | 21-day payment terms, enforced. A trainer paid late does not come back |
| Poor logistics — bad rooms, no breakout space, cohorts larger than agreed | Room standard enforced; go/no-go discipline |
| No feedback | Annual observation with a written conversation |
| Being treated as a supplier rather than a colleague | Quarterly trainer forum; consultation on curriculum change |
| No appointments materialising after empanelment was implied | Do not imply appointments that will not come. Be exact at recruitment |

# 5. The certification pathway

| Stage | Duration | Content | Output |
| --- | --- | --- | --- |
| 1. Identification and approach | — | Source per section 3; initial conversation | Expression of interest |
| 2. Screening | 2 weeks | CV, practice log, references, conduct declaration, conflicts | Shortlist |
| 3. Gap assessment | 1 week | Which of 40-hour, 20-hour, practice, T-TTT are missing | Individual pathway |
| 4. Bridging | 0–6 months | Whatever is missing. Faculty usually need practice; practitioners usually need T-TTT | Prerequisites met |
| 5. T-TTT | 3 days | Adult learning; session plan design; running a debrief; drill design; assessing skill; managing a difficult room; Equator's method and materials | Assessed |
| 6. Shadow delivery | 1 programme | Co-facilitate with a Principal; observed | Observation report |
| 7. Certification | — | Curriculum & Certification Committee | Associate or Lead |
| 8. First solo delivery | — | Observed by the Head of Curriculum | Confirmation |
| 9. Maintenance | Annual | Observation; calibration; CPD | Currency retained |

Total elapsed time from approach to Lead: 4 to 9 months. This is why the bench must be started in month 1 and not when the first student cohort is sold.

## 5.1 T-TTT — what it actually covers

| Day | Content |
| --- | --- |
| 1 | How adults learn a skill; why lecturing fails; the one-third rule; Equator's curriculum architecture; the session plan and how to work to it |
| 2 | Running a simulation and running a debrief. Half the programme. Participants run debriefs and are critiqued. Handling the participant who performed badly; handling the one who thinks they did well |
| 3 | Assessing skill against a rubric; calibration; behavioural anchors; managing a difficult room; records, conduct and boundaries; assessed teaching practice |

Pass standard: 60% aggregate. The pass rate is expected to be around 70%; do not manage it upward. A trainer who cannot run a debrief will damage a cohort and a partnership.

# 6. Bench targets

Rule: no student certificate course is sold in a city with fewer than four certified trainers, of whom at least one is a Lead.

|  | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- |
| Bengaluru — first bench city | 6 (2 Lead) | 9 (3 Lead) | 11 (4 Lead) |
| Pune / Mumbai | 0 | 6 (2 Lead) | 9 (3 Lead) |
| Delhi NCR | 0 | 0 | 6 (2 Lead) |
| Hyderabad | 0 | 0 | 4 (1 Lead) |
| National — Principal and specialist | 2 | 3 | 4 |
| Total certified | 8 | 18 | 34 |
| Student cohorts supportable | 0 | 8 | 22 |

Why Bengaluru first: six target institutions within 90 minutes including two Tier 1 anchor candidates; an established court-annexed centre from which to recruit; and Equator's own case volume in the city. See 01.8 section 9.

# 7. Cost of building the bench

## 7.1 Year 1

| Line | Basis | Amount |
| --- | --- | --- |
| Recruitment and outreach | Travel to centres, meetings, materials | 40,000 |
| T-TTT delivery, one cohort of 12 | Principal 3 days ₹22,000; associate 3 days ₹9,000; materials 12 × ₹800; venue and refreshments | 1,07,000 |
| Bridging support for candidates lacking prerequisites | Subsidised places on T-40 and T-20 for 5 candidates | 60,000 |
| Shadow delivery — half fee for co-facilitation, 8 programme-days | 8 × ₹7,500 | 60,000 |
| Observation and certification | 12 observations × ₹5,000 | 60,000 |
| Trainer toolkit — materials, session plans, assessment sets | Per trainer | 25,000 |
| Trainer forum, calibration, CPD | Two sessions | 50,000 |
| Total |  | 4,02,000 |

This is the ₹4,00,000 line in the year 1 budget at 01.6 section 4.1. It is an investment, not an overhead, and should be presented to the Board as such.

## 7.2 Ongoing, per certified trainer

| Line | Annual |
| --- | --- |
| Annual observation | 5,000 |
| Calibration sessions | 6,000 |
| Trainer forum, four per year | 4,000 |
| CPD contribution | 8,000 |
| Materials refresh | 3,000 |
| Total maintenance | 26,000 |

At 34 trainers in year 3 that is ₹8.8 lakh of maintenance a year. It is not optional; a bench that is not maintained decays into a list of names.

## 7.3 Payback per trainer

|  | Amount |
| --- | --- |
| Cost to certify one trainer | ~₹33,500 (bench build ÷ 12) |
| Annual maintenance | ₹26,000 |
| Contribution generated by 16 programme-days | ~₹1,90,000 |
| Payback | Within the first four programme-days |

# 8. Ninety-day recruitment plan — Bengaluru

| Week | Action | Owner | Output |
| --- | --- | --- | --- |
| 1 | Map every court-annexed centre, LSA and mediation body in Bengaluru; identify coordinators | Head of Curriculum | Contact list |
| 2 | Written approach to each coordinator; request to address their mediator panel | HoC | 4 meetings |
| 3–4 | Present to mediator panels; collect expressions of interest | HoC | 25 EOIs |
| 5 | Screening — CVs, practice logs, references, conduct declarations | HoC + Ops | 16 shortlisted |
| 6 | Individual conversations; gap assessment; be honest about how many days are realistically available | HoC | 12 accepted |
| 7 | Bridging pathways agreed; subsidised places allocated | HoC | Pathways issued |
| 8 | Engagement agreements executed (03.6) | Legal | 12 signed |
| 9–10 | T-TTT cohort delivered | Principal | 12 assessed |
| 11 | Certification decisions | Curriculum Committee | 8–9 certified |
| 12 | Shadow delivery scheduled; first solo deliveries diarised | Ops | Bench live |

Expected conversion: 25 expressions of interest → 12 into T-TTT → 8 to 9 certified. Plan the funnel at 3:1.

# 9. Governance

| Matter | Owner |
| --- | --- |
| Bench strategy and city targets | Programme Director |
| Recruitment, screening, certification | Head of Curriculum & Certification |
| Certification decisions | Curriculum & Certification Committee |
| Allocation to programmes | Manager — Programme Operations |
| Observation and calibration | Head of Curriculum |
| Fees and payment | Finance |
| Conduct and conflicts | Programme Director; General Counsel for serious matters |

## 9.1 Bench register

Maintained in the registers workbook. Fields: name, base city, tier, programmes certified to deliver, T-TTT date, assessor certification, last observation and score, CPD hours, days delivered year to date, availability, conflicts declared, status.

Reviewed monthly. A trainer with no delivery in twelve months is contacted; if the position is unlikely to change, they are moved to inactive with courtesy and remain on the panel of neutrals.

# 10. What must be true

| # | Condition | By | If it fails |
| --- | --- | --- | --- |
| 1 | Bengaluru mapped and coordinators approached | Month 1 | Everything slips a quarter |
| 2 | 25 expressions of interest | Month 2 | Widen sources; include faculty from the first FDPs |
| 3 | T-TTT designed and materials complete | Month 2 | T-TTT cannot run. This is a hard prerequisite alongside the simulation packs |
| 4 | 8 trainers certified in Bengaluru | Month 6 | Student cohorts slip to year 3; year 2 revenue falls ~₹21 lakh |
| 5 | Trainer payment at 21 days from month 1 | Continuous | Attrition, and the reputation is very hard to recover |
| 6 | First trainer forum held | Month 7 | Bench becomes a list rather than a group |