EQUATOR RESOLUTION

An Infrabyx Group venture  ·  www.equatorresolution.com

UNIVERSITY & ACADEMIC PARTNERSHIP PROGRAMME

Training Delivery SOP

From confirmed date to issued certificate — the operational sequence for every training programme

| Document reference | EQ-UAP-075 |
| --- | --- |
| Document family | Operations |
| Version | v1.0 · Draft for legal sign-off |
| Date of issue | July 2026 |
| Law stated as at | 22 July 2026 |
| Owner | Director — Academic Partnerships, Equator ADR Institute |
| Approver | Managing Director, Equator Resolution |
| Classification | Confidential — Internal |

Not legal advice.  This document is a working draft prepared for Equator Resolution. Before it is used with any institution, student or party it must be reviewed by qualified counsel and, where personal data is involved, by the Data Protection Officer. Items marked [verify] must be cleared in the Master Legal Sign-off Register.

Document control

Version history

| Version | Date | Author | Summary of change | Status |
| --- | --- | --- | --- | --- |
| 0.1 | July 2026 | Equator ADR Institute | Initial drafting | Superseded |
| 1.0 | July 2026 | Equator ADR Institute | First complete issue for legal review | Draft for legal sign-off |

Review and approval

| Role | Name | Responsibility | Signature / date |
| --- | --- | --- | --- |
| Preparer | [●] | Drafting and factual accuracy |  |
| Reviewer — Legal | [●] | Statutory compliance; clause risk |  |
| Reviewer — Finance | [●] | Pricing, tax and revenue treatment |  |
| Data Protection Officer | [●] | DPDP Act 2023 and Rules 2025 compliance |  |
| Approver | [●] | Final approval for issue |  |

Distribution and related documents

| Item | Detail |
| --- | --- |
| Primary distribution | Managing Director; Director — Academic Partnerships; Legal; Finance |
| Counterparty distribution | Not for external release without approval |
| Related documents | See 00 — READ ME, University Partnership Programme |
| Retention | 7 years from expiry of the related MOU, unless a longer statutory period applies |
| Review cycle | Annual, or on any change of law affecting the subject matter |

Contents

This table of contents is a live field. Open in Word, select all (Ctrl+A) and press F9 to populate or refresh it.

…

# 1. The sequence

| Days out | Step | Owner |
| --- | --- | --- |
| −45 | Dates confirmed in writing with the institution; entered in the master calendar | Operations |
| −45 | Trainer bench checked and provisionally booked | Curriculum |
| −42 | Purchase order requirement confirmed; advance invoice raised if applicable | Finance |
| −40 | Registration opens; DPDP-compliant notice and consent live on the form | Operations |
| −35 | Room requirement communicated to the institution in writing, with the layout diagram | Operations |
| −30 | Trainers confirmed and engagement letters issued (L-15) | Curriculum |
| −21 | Registration checkpoint. If numbers are below the economic floor, escalate | Operations |
| −14 | Materials quantities fixed; printing ordered | Operations |
| −10 | Trainer travel and accommodation booked | Operations |
| −7 | Final registration count; go or no-go decision | Operations + Director |
| −5 | Participant joining instructions issued | Operations |
| −3 | Materials despatched or handed to the trainer | Operations |
| −2 | Room confirmed with the institution; layout reconfirmed | Operations |
| −1 | Trainer walkthrough of the venue | Trainer |
| 0 | Delivery | Trainer |
| +2 | Feedback collated | Operations |
| +5 | Marks submitted by assessors | Trainers |
| +10 | Moderation completed | Curriculum |
| +12 | Results released | Curriculum |
| +14 | Certificates issued; register updated | Curriculum |
| +21 | Report to the institution | Operations |
| +30 | Revenue share settled or final invoice raised | Finance |

# 2. Go or no-go at day −7

| Condition | Decision |
| --- | --- |
| Registrations at or above minimum cohort | Go |
| Registrations at 80–99% of minimum | Go, with the Director's approval, recorded |
| Registrations below 80% of minimum | No-go. Options: postpone by one cycle; combine with another institution's cohort; convert to institution-paid block delivery; cancel |
| Trainer unavailable and no certified substitute | No-go; reschedule |
| Room unsuitable and no alternative | No-go; reschedule |
| Purchase order not received where required | Director decides; default is defer |

A no-go decision is communicated to the institution the same day, in writing, with the proposed alternative.

# 3. Room standard

| Programme | Requirement |
| --- | --- |
| Skills training up to 30 | Plenary with movable furniture, cabaret or U-shape; three breakout rooms; projector; whiteboard; flip charts |
| Workshop up to 45 | Movable furniture preferred; two breakout rooms; projector; public address |
| Lecture over 50 | Theatre; projector; public address; radio microphone |

A fixed-bench lecture theatre cannot host skills training. If that is what is offered, the programme is postponed. Delivering a mediation simulation in a tiered hall produces a poor first impression that costs more than a rescheduling does.

# 4. On the day

| Time | Action | Owner |
| --- | --- | --- |
| −60 min | Trainer on site; room check; materials laid out; technology tested | Trainer |
| −30 min | Registration desk open; attendance sheet ready; name cards out | Operations or institutional coordinator |
| −10 min | Institution's coordinator briefed on timings, breaks and meals | Trainer |
| Start | Ground rules, learning contract, confidentiality undertakings signed | Trainer |
| Each session | Attendance recorded | Trainer |
| End of each day | Feedback collected; session log completed; any incident recorded and reported | Trainer |
| Final day | Assessment conducted; scripts and sheets collected and secured | Trainer |
| Close | Materials collected; nothing left at the venue; thanks to the institutional coordinator | Trainer |

# 5. Attendance

Rule

Recorded at every session, not once a day

The register is the record; a participant not on it did not attend

Attendance gates are stated in 05.7 and are not waived

A participant below the gate is not assessed and is offered transfer to a later cohort

The register is signed by the trainer and retained for seven years

# 6. Assessment logistics

Rule

Assessors attend the calibration session before any assessed cohort

Scripts are anonymised by candidate number where practicable

Simulation assessments are scheduled with at least 15 minutes between candidates

Where numbers permit, a candidate is not assessed by the trainer who taught them

Scripts and sheets are secured immediately and are never left in a room

Marks are submitted within five days

Nothing is disclosed to a candidate on the day

# 7. Feedback

Rule

Collected at the end of each day, not only at the end of the programme

Anonymous; digital where possible

Analysed within two days

A mean below 3.8 of 5 triggers a review by the Head of Curriculum

A specific complaint about a trainer is escalated the same day

Free-text comments are read in full, not summarised by score alone

Included in the report to the institution in analysed form

# 8. The report to the institution — due within 21 days

| Section | Content |
| --- | --- |
| 1 | Programme, dates, venue, trainers |
| 2 | Registered, attended, completed, certified — four separate numbers |
| 3 | Attendance analysis |
| 4 | Assessment outcomes: distribution, pass rate, notable performances |
| 5 | Feedback analysis with quantitative scores and themes |
| 6 | Photographs, subject to consent |
| 7 | Issues encountered and how they were resolved |
| 8 | Recommendations for the next cohort |
| 9 | Annexure: attendance register and certificate list |

This report is what the institution places in its own accreditation file. It is therefore a deliverable, not an internal courtesy, and it is late at day 22.

# 9. Incidents

| Incident | Action |
| --- | --- |
| Participant injury or illness | First aid; institution informed immediately; incident report same day; insurer notified if material |
| Safeguarding concern | Safeguarding protocol; Director informed within 24 hours |
| Allegation of harassment | POSH protocol; do not investigate informally |
| Trainer unable to continue | Substitute from the bench; if none, suspend and reschedule; institution informed the same day |
| Room withdrawn mid-programme | Escalate to the Nodal Officer; alternative sought; if none, suspend and reschedule |
| Disruptive participant | Trainer speaks privately; if unresolved, exclusion with the Director's approval; institution informed |
| Suspected malpractice in assessment | Do not confront in the room; secure the evidence; report to the Head of Curriculum |
| Confidentiality breach | Report to the Director and to Legal immediately |

Every incident is recorded the same day, whatever its apparent seriousness at the time.