EQUATOR RESOLUTION

An Infrabyx Group venture  ·  www.equatorresolution.com

UNIVERSITY & ACADEMIC PARTNERSHIP PROGRAMME

Event Management SOP

Planning, approval, delivery and reconciliation for conferences, roundtables, Mediation Week, community camps and residential schools

| Document reference | EQ-UAP-076 |
| --- | --- |
| Document family | Operations |
| Version | v1.0 · Draft for legal sign-off |
| Date of issue | July 2026 |
| Law stated as at | 22 July 2026 |
| Owner | Director — Academic Partnerships, Equator ADR Institute |
| Approver | Managing Director, Equator Resolution |
| Classification | Confidential — Internal |

Not legal advice.  This document is a working draft prepared for Equator Resolution. Before it is used with any institution, student or party it must be reviewed by qualified counsel and, where personal data is involved, by the Data Protection Officer. Items marked [verify] must be cleared in the Master Legal Sign-off Register.

Document control

Version history

| Version | Date | Author | Summary of change | Status |
| --- | --- | --- | --- | --- |
| 0.1 | July 2026 | Equator ADR Institute | Initial drafting | Superseded |
| 1.0 | July 2026 | Equator ADR Institute | First complete issue for legal review | Draft for legal sign-off |

Review and approval

| Role | Name | Responsibility | Signature / date |
| --- | --- | --- | --- |
| Preparer | [●] | Drafting and factual accuracy |  |
| Reviewer — Legal | [●] | Statutory compliance; clause risk |  |
| Reviewer — Finance | [●] | Pricing, tax and revenue treatment |  |
| Data Protection Officer | [●] | DPDP Act 2023 and Rules 2025 compliance |  |
| Approver | [●] | Final approval for issue |  |

Distribution and related documents

| Item | Detail |
| --- | --- |
| Primary distribution | Managing Director; Director — Academic Partnerships; Legal; Finance |
| Counterparty distribution | Not for external release without approval |
| Related documents | See 00 — READ ME, University Partnership Programme |
| Retention | 7 years from expiry of the related MOU, unless a longer statutory period applies |
| Review cycle | Annual, or on any change of law affecting the subject matter |

Contents

This table of contents is a live field. Open in Word, select all (Ctrl+A) and press F9 to populate or refresh it.

…

# 1. Gate discipline

| Gate | Requirement | Cannot proceed without |
| --- | --- | --- |
| G1 — Concept | Written concept passing the three-outcome test; indicative budget | Director's approval |
| G2 — Budget | Full budget per 04.4; cost-split agreed in writing with the host | Approval at the correct threshold |
| G3 — Plan | Event plan complete; speakers provisionally confirmed; venue confirmed | Director's approval |
| G4 — Announce | Date, venue, speakers and registration ready | No announcement before G4 |
| G5 — Go | Registration at threshold; speakers confirmed in writing; safety arrangements confirmed | Director's approval |
| G6 — Close | Post-event report and financial reconciliation | Within 30 days |

The rule broken most often is G4. An event announced before its budget and venue are confirmed generates commitments that cannot be withdrawn.

# 2. Timeline for a major event

| Weeks out | Task |
| --- | --- |
| 16 | Concept approved (G1); date fixed against the academic and national calendar |
| 14 | Budget approved (G2); Schedule D cost-split agreed with the host in writing |
| 13 | Venue confirmed; walkthrough conducted |
| 12 | Speaker and dignitary invitations issued |
| 10 | Sponsorship approach begins; screening protocol applied |
| 9 | Event plan complete (G3) |
| 8 | Announcement and registration opens (G4) |
| 8 | Judicial and public authority invitations issued, where applicable, with lead time |
| 6 | Branding and production briefed |
| 5 | Speaker confirmations in writing; bios and photographs collected |
| 4 | Run sheet drafted; roles allocated |
| 3 | Volunteer recruitment and briefing scheduled with the host |
| 2 | Materials printed; delegate kits assembled |
| 2 | Registration checkpoint; G5 decision |
| 1 | Final walkthrough; contingency confirmed; first aid and emergency route posted |
| 1 | Speaker liaison confirms travel, arrival and requirements |
| 0 | Delivery |
| +1 | Thanks issued (L-21); photographs distributed |
| +4 | Post-event report and reconciliation (G6) |

# 3. The event plan

| Section | Content |
| --- | --- |
| Objective and the outcome it serves | Pipeline, credibility or revenue |
| Audience and expected attendance | With the basis of the estimate |
| Date, venue, layout and capacity | Diagram attached |
| Run sheet | Minute by minute, with owners |
| Budget and cost-split | Per 04.4 |
| Speakers and dignitaries | Confirmed status, travel, requirements |
| Branding and media plan | Approved creative |
| Registration and data protection | Notice and consent form approved |
| Safety, first aid, emergency route | Confirmed with the host |
| Safeguarding, where minors attend | Supervision ratio, consents |
| Contingency plans | Weather, power, speaker absence, low attendance |
| Named owners | For each element |

# 4. Dignitaries and public authorities

Rule

Invitations to judicial officers, public authorities or dignitaries require the Programme Director's approval and are issued with not less than eight weeks' lead time

Neither party invites in the other's name without prior written approval

No fee, honorarium or gift is offered to a public official except as permitted by law and by the anti-bribery obligations

Protocol requirements — seating, precedence, security, timing — are confirmed with the office concerned in writing

A named liaison is assigned to each dignitary for the day

Programmes state names, designations and precedence exactly as confirmed by the office

# 5. Residential events

Residential formats carry materially higher duty of care.

Requirement

Accommodation inspected in advance; separate arrangements by gender; supervision arrangements agreed

A named residential coordinator on duty and contactable 24 hours

Emergency contact for every participant collected at registration

Medical information and allergies collected; nearest hospital identified and posted

Separate written consent for residential participation; guardian consent where under eighteen

Curfew and conduct rules issued in advance and acknowledged

No alcohol at any Equator residential event

Incident and escalation route posted in every room

Ratio of at least one supervising adult to fifteen participants; two-adult rule where minors attend

# 6. Community and outreach events

Rule

Conducted with the District Legal Services Authority or an equivalent authority wherever possible, not independently

No legal advice is given to any member of the public; signposting only

No personal data collected beyond what is necessary, and only with a clear notice in the local language

Students participate under supervision and do not advise

No photography of any member of the public without consent, and none of any person in a vulnerable situation

Materials in the local language

A written report to the authority afterwards

# 7. Safety

| Item | Owner |
| --- | --- |
| Fire safety, egress, crowd management, structural safety of the premises | Host institution |
| First aid provision and a named first aider | Host institution |
| Nearest hospital identified, route posted in every room | Equator, confirmed with host |
| Emergency contact list, including the host's security | Equator |
| Public liability insurance in force | Equator, per the MOU |
| Incident reporting within 24 hours | Equator |

Before every event, Operations confirms these in writing with the host. A confirmation not received in writing is treated as not received.

# 8. On the day

| Time | Action |
| --- | --- |
| −180 min | Venue handover; signage and branding installed |
| −120 min | Registration desk; delegate kits; seating plan |
| −90 min | Audio-visual tested end to end, with the actual presentation files |
| −60 min | Volunteer briefing; roles and boundaries; first aid point confirmed |
| −45 min | Speaker liaison confirms arrivals |
| −30 min | Registration opens |
| Throughout | Run sheet followed; owner of each item present; photographer working to the shot list |
| Close | Thanks; feedback collected; contact details captured with consent |
| +60 min | Pack down; venue returned; nothing left behind |
| Same day | Incident log completed, even if nil |

# 9. Post-event

| Deliverable | Due |
| --- | --- |
| Thanks to the host and to key contributors (L-21) | 7 days |
| Photographs distributed | 14 days |
| Feedback analysis | 14 days |
| Attendance and outcome report to the host institution | 21 days |
| Sponsor reports | 30 days |
| Financial reconciliation and variance explanation | 30 days |
| Lessons learned, with three changes for next time | 30 days |
| Follow-up on leads generated — enquiries, institutions, sponsors | 14 days |

The follow-up on leads is the item most often skipped and the one that determines whether the event was worth running.