EQUATOR RESOLUTION

An Infrabyx Group venture  ·  www.equatorresolution.com

UNIVERSITY & ACADEMIC PARTNERSHIP PROGRAMME

Risk Register & Escalation Matrix

The programme's risks, scored, owned and mitigated, with the escalation route for each severity level

| Document reference | EQ-UAP-080 |
| --- | --- |
| Document family | Operations |
| Version | v1.0 · Draft for legal sign-off |
| Date of issue | July 2026 |
| Law stated as at | 22 July 2026 |
| Owner | Director — Academic Partnerships, Equator ADR Institute |
| Approver | Managing Director, Equator Resolution |
| Classification | Confidential — Internal |

Not legal advice.  This document is a working draft prepared for Equator Resolution. Before it is used with any institution, student or party it must be reviewed by qualified counsel and, where personal data is involved, by the Data Protection Officer. Items marked [verify] must be cleared in the Master Legal Sign-off Register.

Document control

Version history

| Version | Date | Author | Summary of change | Status |
| --- | --- | --- | --- | --- |
| 0.1 | July 2026 | Equator ADR Institute | Initial drafting | Superseded |
| 1.0 | July 2026 | Equator ADR Institute | First complete issue for legal review | Draft for legal sign-off |

Review and approval

| Role | Name | Responsibility | Signature / date |
| --- | --- | --- | --- |
| Preparer | [●] | Drafting and factual accuracy |  |
| Reviewer — Legal | [●] | Statutory compliance; clause risk |  |
| Reviewer — Finance | [●] | Pricing, tax and revenue treatment |  |
| Data Protection Officer | [●] | DPDP Act 2023 and Rules 2025 compliance |  |
| Approver | [●] | Final approval for issue |  |

Distribution and related documents

| Item | Detail |
| --- | --- |
| Primary distribution | Managing Director; Director — Academic Partnerships; Legal; Finance |
| Counterparty distribution | Not for external release without approval |
| Related documents | See 00 — READ ME, University Partnership Programme |
| Retention | 7 years from expiry of the related MOU, unless a longer statutory period applies |
| Review cycle | Annual, or on any change of law affecting the subject matter |

Contents

This table of contents is a live field. Open in Word, select all (Ctrl+A) and press F9 to populate or refresh it.

…

# 1. Scoring

Risk score = Likelihood × Impact, each on a scale of 1 to 5.

| Score | Rating | Treatment |
| --- | --- | --- |
| 20–25 | Critical | Programme Board; mitigation plan with dates; reviewed monthly |
| 12–19 | High | Programme Director; mitigation plan; reviewed quarterly |
| 6–11 | Medium | Owner; controls documented; reviewed half-yearly |
| 1–5 | Low | Monitored |

# 2. The register

## 2.1 Strategic

| # | Risk | L | I | Score | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | MOUs signed but dormant; effort sunk with no return | 4 | 3 | 12 | Minimum activity clause 6.4 with automatic lapse; activation SOP; annual scorecard; capacity ceiling on new signings | Director |
| R2 | Mediation Council notifies standards the curriculum does not meet | 3 | 5 | 15 | Curriculum mapped to court-annexed 40+20 norms; modular design; regulatory watch reported quarterly | Head of Curriculum |
| R3 | Programme fails to reach breakeven in year 2 | 3 | 4 | 12 | Advisory retainers and coaching prioritised; local bench density targets; monthly revenue tracking | Director |
| R4 | Competitor establishes a dominant university network first | 3 | 3 | 9 | Speed; Tier 1 anchors secured early; narrow exclusivity where justified | Director |

## 2.2 Legal and regulatory

| # | Risk | L | I | Score | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R5 | Marketing claim about certification challenged as misleading | 3 | 5 | 15 | Approved formulations only; all collateral cleared by Legal; open item U6 | Legal |
| R6 | Student personal data mishandled under DPDP | 3 | 5 | 15 | Data Addendum; consent architecture; DPO sign-off before any portal; annual training; open item U3 | DPO |
| R7 | Breach of mediation confidentiality by a student or intern | 3 | 5 | 15 | Live clinic SOP; undertakings signed per session; no devices; notes destroyed; 45-minute induction session | Coordinator |
| R8 | Intern characterised as an employee, with statutory consequences | 3 | 4 | 12 | Internship agreement; genuine educational content; stipend policy; open item U4 | HR |
| R9 | GST position determined adversely with retrospective effect | 3 | 4 | 12 | Quote exclusive of tax; no position asserted; open item U1 prioritised | Finance |
| R10 | Conflict of interest — partner institution becomes a party | 3 | 3 | 9 | Conflict policy; entity separation; disclosure and recusal protocol | Legal |
| R11 | Certificate represented as a qualification by a partner | 3 | 4 | 12 | Mandatory statement on every certificate; Schedule G prohibitions; monitoring of partner collateral | Marketing |

## 2.3 Safeguarding and conduct

| # | Risk | L | I | Score | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R12 | Safeguarding incident involving a student | 2 | 5 | 10 | Safeguarding policy; two-adult rule; trained staff; 24-hour escalation; residential protocols | Operations |
| R13 | Harassment allegation against a trainer or staff member | 2 | 5 | 10 | Code of conduct; POSH machinery; complaints bypass; no informal investigation | Director |
| R14 | Incident at a residential event | 2 | 4 | 8 | Residential protocol; supervision ratio; no alcohol; 24-hour coordinator; medical information collected | Operations |
| R15 | Trainer misconduct with a participant | 2 | 5 | 10 | Engagement agreement clause 7; declaration; observation; feedback route | Curriculum |

## 2.4 Operational

| # | Risk | L | I | Score | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R16 | Key-person dependency on a small trainer bench | 4 | 4 | 16 | Train-the-trainer; minimum bench of 12 before scaling; local bench targets per city | Curriculum |
| R17 | Cohort under-subscription; programme uneconomic | 4 | 3 | 12 | Free guest lecture first; day −21 and −7 checkpoints; combine cohorts; go/no-go discipline | Operations |
| R18 | Unsuitable venue delivered on the day | 3 | 3 | 9 | Room standard communicated in writing at −35; walkthrough at −1; postpone rather than deliver badly | Operations |
| R19 | Competition integrity failure — leak, disputed result | 2 | 5 | 10 | Integrity architecture; separations; calibration; appeals with a defined route | Convenor |
| R20 | Trainer unavailable at short notice | 3 | 3 | 9 | Reserve bench; substitution protocol; institution informed same day | Curriculum |

## 2.5 Financial

| # | Risk | L | I | Score | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R21 | Free-of-cost creep; paid programmes given away | 4 | 3 | 12 | Delegation of Authority; approved loss leaders only; exceptions register reported quarterly | Finance |
| R22 | Revenue share not settled by an institution | 3 | 3 | 9 | Preference for Equator collection; settlement SOP; escalation ladder; no new delivery beyond 60 days overdue | Finance |
| R23 | Competition deficit exceeding budget | 3 | 3 | 9 | No launch without title sponsor contracted; 10% contingency; edition 1 ceiling of ₹2.5 lakh | Convenor |
| R24 | Receivables ageing beyond 90 days | 3 | 3 | 9 | Collections ladder; purchase order discipline; standing rule on further delivery | Finance |

## 2.6 Reputational

| # | Risk | L | I | Score | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R25 | Poorly delivered programme at a visible institution | 3 | 4 | 12 | Quality thresholds; observation; feedback daily; suspension protocol below 3.5 | Curriculum |
| R26 | Sponsor association damages the brand | 2 | 4 | 8 | Sponsor screening protocol; excluded sectors; host institution consulted | Director |
| R27 | Public dispute with a partner institution | 2 | 4 | 8 | Escalation ladder; mediation-first dispute clause; publicity clause 21.8 | Director |

# 3. Escalation matrix

| Level | Trigger | To whom | Timeframe | Record |
| --- | --- | --- | --- | --- |
| L1 | Routine delivery issue — scheduling, materials, logistics | Manager, Programme Operations | 2 working days | Session log |
| L2 | Partner dissatisfaction; assessment dispute; feedback below 3.8; calendar slippage | Programme Director | 5 working days | Incident log |
| L3 | Contractual dispute; pricing concession sought; competition integrity challenge; receivable beyond 60 days; media enquiry | Programme Board | 10 working days | Board paper |
| L4 | Safeguarding incident · data breach · confidentiality breach involving a real party · regulatory contact · litigation threat · allegation against a staff member | Managing Director and General Counsel immediately; Board notified | Same day | Formal incident report; permanent retention |

## 3.1 L4 — immediate actions

Ensure the safety of any person at risk. Nothing else takes priority.

Notify the Managing Director and General Counsel by telephone, not email.

Notify the DPO within one hour where personal data is involved.

Preserve all evidence; change nothing.

Do not investigate informally; do not interview; do not take a statement.

Do not communicate externally. All communication is by the Managing Director.

Written incident report within 24 hours.

Notify the partner institution within 24 hours where its students or premises are involved.

Notify the insurer where cover may respond.

Post-incident review within 30 days, with actions and owners.

# 4. Review

| Activity | Frequency | Owner |
| --- | --- | --- |
| Register reviewed and re-scored | Quarterly | Director |
| Critical and high risks reviewed | Monthly | Director |
| New risks added | On identification | Any role-holder |
| Incident log reviewed for emerging risk | Monthly | Director |
| Register presented to the Programme Board | Quarterly | Director |
| Full review including scoring methodology | Annual | Programme Board |