EQUATOR RESOLUTION

An Infrabyx Group venture  ·  www.equatorresolution.com

UNIVERSITY & ACADEMIC PARTNERSHIP PROGRAMME

Joint Steering Committee Charter & Terms of Reference

Composition, authority, meeting discipline and the limits of what the Committee may decide

| Document reference | EQ-UAP-090 |
| --- | --- |
| Document family | Governance |
| Version | v1.0 · Draft for legal sign-off |
| Date of issue | July 2026 |
| Law stated as at | 22 July 2026 |
| Owner | Director — Academic Partnerships, Equator ADR Institute |
| Approver | Managing Director, Equator Resolution |
| Classification | Confidential — Internal and partner institution |

Not legal advice.  This document is a working draft prepared for Equator Resolution. Before it is used with any institution, student or party it must be reviewed by qualified counsel and, where personal data is involved, by the Data Protection Officer. Items marked [verify] must be cleared in the Master Legal Sign-off Register.

Document control

Version history

| Version | Date | Author | Summary of change | Status |
| --- | --- | --- | --- | --- |
| 0.1 | July 2026 | Equator ADR Institute | Initial drafting | Superseded |
| 1.0 | July 2026 | Equator ADR Institute | First complete issue for legal review | Draft for legal sign-off |

Review and approval

| Role | Name | Responsibility | Signature / date |
| --- | --- | --- | --- |
| Preparer | [●] | Drafting and factual accuracy |  |
| Reviewer — Legal | [●] | Statutory compliance; clause risk |  |
| Reviewer — Finance | [●] | Pricing, tax and revenue treatment |  |
| Data Protection Officer | [●] | DPDP Act 2023 and Rules 2025 compliance |  |
| Approver | [●] | Final approval for issue |  |

Distribution and related documents

| Item | Detail |
| --- | --- |
| Primary distribution | Managing Director; Director — Academic Partnerships; Legal; Finance |
| Counterparty distribution | Not for external release without approval |
| Related documents | See 00 — READ ME, University Partnership Programme |
| Retention | 7 years from expiry of the related MOU, unless a longer statutory period applies |
| Review cycle | Annual, or on any change of law affecting the subject matter |

Contents

This table of contents is a live field. Open in Word, select all (Ctrl+A) and press F9 to populate or refresh it.

…

# 1. Purpose

The Joint Steering Committee is the standing body through which a partnership is managed between the parties. It exists so that delivery is reviewed by people with authority, on a fixed rhythm, rather than only when something has gone wrong.

# 2. Composition

| Element | Standard |
| --- | --- |
| Size | Four to six; two to three nominated by each party |
| Mandatory members | Each party's Nodal Officer |
| University side, typically | Nodal Officer; Dean or Head of Department; a faculty member responsible for delivery |
| Equator side, typically | Nodal Officer; Programme Director or Operations Manager; Head of Curriculum where curriculum is on the agenda |
| Chair | Alternates between the parties, meeting by meeting. The first meeting is chaired by the University |
| Secretary | Equator provides the secretary, who circulates papers and minutes |
| Quorum | One member from each party, one of whom must be a Nodal Officer |
| Attendance by others | By invitation, for a specific item |
| Student representation | Recommended — one student who has completed a programme, invited for the delivery and feedback items |

# 3. Authority

## 3.1 The Committee may

review delivery against the Activity Calendar;

agree amendments to the Activity Calendar within the existing schedules;

consider and recommend new activities;

review feedback, quality data and incident reports;

resolve operational issues escalated by the Nodal Officers;

review the partnership scorecard;

make a recommendation on renewal, restructuring or lapse.

## 3.2 The Committee may not

vary the Memorandum of Understanding or any schedule;

agree commercial terms outside Schedule H, or grant any discount;

commit either party to expenditure;

waive the minimum activity commitment;

grant exclusivity;

decide any matter of assessment, certification or competition integrity, which are reserved to Equator's own committees;

decide any safeguarding, POSH or data protection matter, which follow their own protocols.

Where a matter falls outside the Committee's authority, it is recorded and referred, and the referral is minuted.

# 4. Meetings

| Element | Standard |
| --- | --- |
| Frequency | Not fewer than twice each academic year; ordinarily at the start and the end |
| Additional meetings | On the request of either party, on fourteen days' notice |
| Mode | In person or by video conference |
| Duration | 60 to 90 minutes. A steering meeting that runs to three hours has become an operations meeting |
| Papers | Circulated five working days in advance. A meeting proceeds only if papers were circulated; otherwise it is deferred |
| Minutes | Circulated within ten working days; approved at the next meeting |
| Actions | Recorded with an owner and a date, and reviewed at the following meeting |

# 5. Standing agenda

| # | Item | Paper | Minutes |
| --- | --- | --- | --- |
| 1 | Minutes of the last meeting and matters arising | Previous minutes | 5 |
| 2 | Actions from the last meeting | Action log | 5 |
| 3 | Delivery against the Activity Calendar | Delivery report | 15 |
| 4 | Quality and feedback | Feedback analysis | 10 |
| 5 | Participation and outcomes — students trained, certified, interns placed, competition results | Scorecard extract | 10 |
| 6 | Commercial position — activities charged, settled, outstanding | Finance summary | 10 |
| 7 | Issues, risks and incidents | Issue log | 10 |
| 8 | Forward calendar and proposed new activities | Draft calendar | 15 |
| 9 | Any other business | — | 5 |
| 10 | Date of the next meeting | — | 2 |

Item 3 is the meeting. If time runs short, everything else gives way to it.

# 6. Papers

| Paper | Prepared by | Content |
| --- | --- | --- |
| Delivery report | Equator Operations | Every calendared activity: planned, delivered, deferred, cancelled, with reasons |
| Feedback analysis | Equator Operations | Scores by activity; themes; actions taken |
| Scorecard extract | Equator Director | Per 10.2 |
| Finance summary | Equator Finance | Activities charged, invoiced, settled, outstanding; revenue-share position |
| Issue log | Both Nodal Officers | Open issues, owner, status, age |
| Draft calendar | Equator Operations | Next period, with prerequisites and dependencies |

# 7. Escalation

| Level | Route |
| --- | --- |
| 1 | Nodal Officers, within ten working days |
| 2 | Joint Steering Committee, at its next meeting or at a special meeting |
| 3 | Registrar of the University and Programme Director of Equator |
| 4 | Per clause 18 of the Memorandum — mediation, then arbitration |

A matter is not escalated to level 3 without first being minuted at level 2, save where it is urgent or falls within the L4 categories.

# 8. Annual review

Not less than ninety days before the end of each academic year, the Committee conducts a written annual review using the template at 10.3, covering delivery, participation, outcomes, quality, commercials, issues and a recommendation on renewal.

The recommendation is advisory. The decision rests with the Registrar and the Programme Director, under their respective delegations.

# 9. First meeting agenda

The first meeting after activation is different and follows this agenda:

Introductions, and confirmation of the members and the Nodal Officers.

What we have agreed — walk through the executed schedules together, out loud. Assumptions surface here that would otherwise surface in year two.

The signed first-year Activity Calendar; confirm dependencies and prerequisites.

Facilities: what is available, how it is booked, and who to contact.

Communications and approvals: who approves what, and how quickly.

Commercials: purchase orders, invoicing, contacts, timing.

Data protection contacts and the position on the Addendum.

How we will handle a problem: the escalation route, agreed while everyone is content.

Measures: what we will report to each other, and how often.

Dates for the next two meetings, fixed now.

Item 8 is agreed at the first meeting deliberately. It is far easier to agree how to disagree before anyone has.