EQUATOR RESOLUTION

An Infrabyx Group venture  ·  www.equatorresolution.com

UNIVERSITY & ACADEMIC PARTNERSHIP PROGRAMME

Renewal, Exit & Wind-Down SOP

Deciding whether to renew, how to let a partnership lapse well, and how to wind one down without damage

| Document reference | EQ-UAP-093 |
| --- | --- |
| Document family | Governance |
| Version | v1.0 · Draft for legal sign-off |
| Date of issue | July 2026 |
| Law stated as at | 22 July 2026 |
| Owner | Director — Academic Partnerships, Equator ADR Institute |
| Approver | Managing Director, Equator Resolution |
| Classification | Confidential — Internal |

Not legal advice.  This document is a working draft prepared for Equator Resolution. Before it is used with any institution, student or party it must be reviewed by qualified counsel and, where personal data is involved, by the Data Protection Officer. Items marked [verify] must be cleared in the Master Legal Sign-off Register.

Document control

Version history

| Version | Date | Author | Summary of change | Status |
| --- | --- | --- | --- | --- |
| 0.1 | July 2026 | Equator ADR Institute | Initial drafting | Superseded |
| 1.0 | July 2026 | Equator ADR Institute | First complete issue for legal review | Draft for legal sign-off |

Review and approval

| Role | Name | Responsibility | Signature / date |
| --- | --- | --- | --- |
| Preparer | [●] | Drafting and factual accuracy |  |
| Reviewer — Legal | [●] | Statutory compliance; clause risk |  |
| Reviewer — Finance | [●] | Pricing, tax and revenue treatment |  |
| Data Protection Officer | [●] | DPDP Act 2023 and Rules 2025 compliance |  |
| Approver | [●] | Final approval for issue |  |

Distribution and related documents

| Item | Detail |
| --- | --- |
| Primary distribution | Managing Director; Director — Academic Partnerships; Legal; Finance |
| Counterparty distribution | Not for external release without approval |
| Related documents | See 00 — READ ME, University Partnership Programme |
| Retention | 7 years from expiry of the related MOU, unless a longer statutory period applies |
| Review cycle | Annual, or on any change of law affecting the subject matter |

Contents

This table of contents is a live field. Open in Word, select all (Ctrl+A) and press F9 to populate or refresh it.

…

# 1. Principle

Letting a partnership end is a normal, healthy management action, not a failure. A programme with sixty-eight partnerships of which twelve are dormant is worse off than one with fifty-six that are active, because the dormant twelve consume attention, distort reporting and dilute the brand.

The purpose of this SOP is to make ending a partnership as ordinary and as well-executed as starting one.

# 2. Renewal timeline

| Days before expiry | Step | Owner |
| --- | --- | --- |
| 150 | Renewal flagged from the diary entry created at activation | Operations |
| 135 | Scorecard prepared | Director |
| 120 | Annual review drafted | Director |
| 110 | Steering Committee considers the review and makes a recommendation | Committee |
| 100 | Internal decision under the Delegation of Authority | Director / Board |
| 90 | Renewal notice (L-19) or non-renewal notice (L-20) issued | Director |
| 75 | Renewal terms negotiated; schedules revised | BD |
| 45 | Renewal instrument issued for execution | Legal |
| 15 | Executed | Both |
| 0 | New term commences; calendar for the coming year already agreed | Operations |

The reason the decision is taken at day 100 rather than day 30 is that the coming academic year's calendar must be agreed before the institution's own planning closes. A renewal signed a week before expiry produces a year with no activities in the first term.

# 3. The decision

| Scorecard result | Default decision |
| --- | --- |
| 8 or 9 tests passed | Renew; consider promotion a tier |
| 6 or 7 passed | Renew as is; address the failed tests in the calendar |
| 4 or 5 passed | Restructure to a lower tier |
| 3 or fewer, first year | Restructure to Tier 3, with a specific recovery plan |
| 3 or fewer, two consecutive years | Allow to lapse |
| Any failure of T9 (compliance) | Escalate to the Programme Board irrespective of other tests |
| No champion (T7) for two years | Restructure to Tier 3 |

Overriding considerations requiring Programme Board approval: geographic importance where Equator has no other presence; brand value disproportionate to revenue; a Tier 1 termination; or a partnership where an incident has occurred.

# 4. Restructuring rather than terminating

Restructuring is usually better than termination. It preserves the relationship, reduces effort to a proportionate level, and leaves the door open.

| From | To | What changes |
| --- | --- | --- |
| Tier 1 | Tier 2 | ADR Laboratory naming ends; research chair ends; exclusivity ends; hosting rights become participation; effort norm falls from 104 to 39 person-days |
| Tier 2 | Tier 3 | Paid programmes cease unless separately contracted; internship allocation becomes open application; webinars and competitions continue |
| Any tier | Tier 3 | The relationship continues at near-zero cost to both |

Restructuring is effected by a written variation to the schedules; the body of the MOU is unaffected. It should be presented honestly: the collaboration has not developed as either of us expected, and rather than let it sit unused we propose to simplify it to the things that are working.

# 5. Letting a partnership lapse

Where clause 6.4 has operated, or where the parties agree not to renew:

| Step | Action |
| --- | --- |
| 1 | Non-renewal letter (L-20) issued at day 90, with the annual review attached |
| 2 | Telephone call from the Programme Director to the Nodal Officer before the letter arrives. A letter that arrives unannounced damages the relationship unnecessarily |
| 3 | Activities in progress completed; participants assessed and certified normally |
| 4 | Interns complete their placements |
| 5 | Competition entries already accepted remain valid |
| 6 | Wind-down checklist at section 7 executed |
| 7 | Institution moved to the nurture register; re-approach diarised for 24 months |
| 8 | Lessons recorded in the pipeline review |

Tone. The relationship is with individuals who may move to other institutions. A partnership that ends courteously frequently returns.

# 6. Termination for cause

Reserved for material breach, insolvency, regulatory action, reputational events, or breach of the confidentiality, data, safeguarding or anti-bribery clauses.

| Step | Requirement |
| --- | --- |
| 1 | Programme Director and General Counsel assess against clause 5.4 |
| 2 | Where the breach is capable of remedy, a remedy notice giving 30 days |
| 3 | Where not remediable, or unremedied, termination notice under clause 5.4 |
| 4 | Programme Board informed; Board of Equator Resolution informed for a Tier 1 |
| 5 | All activities suspended immediately pending the wind-down decision |
| 6 | Participants notified of the effect on their programmes, and protected — no participant loses a certificate they have earned because of a dispute between institutions |
| 7 | Communications: holding statement E only; no public comment |
| 8 | Wind-down checklist executed on an accelerated timetable |

# 7. Wind-down checklist

| # | Item | Owner | By |
| --- | --- | --- | --- |
| 1 | Activities in progress identified; completion or transfer plan agreed | Operations | Day 7 |
| 2 | Participants notified in writing of the effect on their programme | Operations | Day 10 |
| 3 | Interns notified; placements completed | Coordinator | Day 10 |
| 4 | Certificates for completed programmes issued | Curriculum | Day 21 |
| 5 | Competition entries confirmed as valid | Convenor | Day 7 |
| 6 | Marks removed from both parties' websites, social media and collateral | Marketing | Day 30 |
| 7 | Campus signage removed; branded items retrieved | Operations | Day 30 |
| 8 | Confidential information returned or destroyed; certification exchanged | Legal | Day 30 |
| 9 | Personal data dealt with per the Data Addendum; erasure certified | DPO | Day 60 |
| 10 | Research data returned or deleted; deletion certified | Research Lead | Day 60 |
| 11 | Final invoices raised; revenue share settled | Finance | Day 30 |
| 12 | Outstanding amounts pursued or written off with approval | Finance | Day 60 |
| 13 | Facilities vacated; keys and access returned | Operations | Day 30 |
| 14 | Fixtures dealt with per Schedule F | Operations | Day 45 |
| 15 | Faculty empanelments reviewed — these ordinarily continue, being personal | Director | Day 30 |
| 16 | Alumni and ambassadors informed; their access continues | Marketing | Day 30 |
| 17 | CRM updated; status changed; re-approach diarised | BD | Day 7 |
| 18 | Partnership file closed and archived; retention date set | Operations | Day 60 |
| 19 | Final letter confirming completion of wind-down | Director | Day 65 |
| 20 | Lessons recorded | Director | Day 60 |

# 8. What continues after the partnership ends

| Item | Position |
| --- | --- |
| Certificates already issued | Valid permanently; verifiable on request |
| The certification register | Retained permanently in minimum form |
| Faculty empanelment | Continues — it is a personal engagement with the individual, not with the institution |
| Alumni access to webinars | Continues |
| Competition eligibility | Continues; institutions need no MOU to enter |
| Student ambassador appointments | Complete their term |
| Confidentiality obligations | Continue per clause 10.6 |
| Statutory confidentiality on live matters | Permanent |
| Jointly owned research | Continues to be usable by both parties per 08.2 |
| Publication of jointly authored work in progress | Completed; neither party may block it |
| Historic factual reference to the collaboration | Permitted, in the past tense, accurately |

# 9. Records

| Record | Retention |
| --- | --- |
| Executed MOU, schedules and variations | 7 years from expiry |
| Annual reviews and scorecards | 7 years |
| Termination or non-renewal correspondence | 7 years |
| Wind-down checklist, signed | 7 years |
| Data erasure certifications | 7 years |
| Certification register | Permanent |
| Safeguarding or incident records arising | Permanent |