EQUATOR RESOLUTION

An Infrabyx Group venture  ·  www.equatorresolution.com

UNIVERSITY & ACADEMIC PARTNERSHIP PROGRAMME

Hiring Plan & Year 1 Operating Budget

Sequence, triggers, line-by-line budget, cash profile and the decision gates that release each hire

| Document reference | EQ-UAP-108 |
| --- | --- |
| Document family | Organisation |
| Version | v1.0 · Draft for legal sign-off |
| Date of issue | July 2026 |
| Law stated as at | 22 July 2026 |
| Owner | Director — Academic Partnerships, Equator ADR Institute |
| Approver | Managing Director, Equator Resolution |
| Classification | Confidential — Internal (Strictly) |

Not legal advice.  This document is a working draft prepared for Equator Resolution. Before it is used with any institution, student or party it must be reviewed by qualified counsel and, where personal data is involved, by the Data Protection Officer. Items marked [verify] must be cleared in the Master Legal Sign-off Register.

Document control

Version history

| Version | Date | Author | Summary of change | Status |
| --- | --- | --- | --- | --- |
| 0.1 | July 2026 | Equator ADR Institute | Initial drafting | Superseded |
| 1.0 | July 2026 | Equator ADR Institute | First complete issue for legal review | Draft for legal sign-off |

Review and approval

| Role | Name | Responsibility | Signature / date |
| --- | --- | --- | --- |
| Preparer | [●] | Drafting and factual accuracy |  |
| Reviewer — Legal | [●] | Statutory compliance; clause risk |  |
| Reviewer — Finance | [●] | Pricing, tax and revenue treatment |  |
| Data Protection Officer | [●] | DPDP Act 2023 and Rules 2025 compliance |  |
| Approver | [●] | Final approval for issue |  |

Distribution and related documents

| Item | Detail |
| --- | --- |
| Primary distribution | Managing Director; Director — Academic Partnerships; Legal; Finance |
| Counterparty distribution | Not for external release without approval |
| Related documents | See 00 — READ ME, University Partnership Programme |
| Retention | 7 years from expiry of the related MOU, unless a longer statutory period applies |
| Review cycle | Annual, or on any change of law affecting the subject matter |

Contents

This table of contents is a live field. Open in Word, select all (Ctrl+A) and press F9 to populate or refresh it.

…

# 1. Principle

Every hire is released by a trigger, not by a date. The triggers below are contracted revenue or delivery volume, both of which are observable. A hire made ahead of its trigger converts a manageable loss into an unmanageable one; a hire made after it costs quality and renewal.

# 2. Hiring sequence

| # | Role | Trigger | Expected timing | Cost, annualised |
| --- | --- | --- | --- | --- |
| 1 | Manager — BD & Programmes | Programme approved | Month 1 | 12,00,000 |
| 2 | Head of Curriculum, retained 0.3 | Programme approved | Month 1 | 7,00,000 |
| 3 | Coordinator — Programmes, 0.4 | 6 programmes contracted | Month 3 | 2,40,000 |
| 4 | Head of Curriculum, to full-time | 15 programmes a year or 12 bench trainers | Month 10–14 | 21,00,000 |
| 5 | Programme Director, to full-time | Contracted forward revenue ≥ ₹1 crore | Month 13–15 | 28,00,000 |
| 6 | Manager — Programme Operations | 20 delivery events a year | Month 14–16 | 11,00,000 |
| 7 | Coordinator — Internships, 0.6 | 15 interns a cycle | Month 15–18 | 5,00,000 |
| 8 | Marketing Executive, 0.5 | Ambassador programme at 4 institutions | Month 6–9 | 4,00,000 |
| 9 | Competition Convenor, 0.5 | Own competition approved for year 2 | Month 16 | 6,50,000 |
| 10 | Research Lead, 0.5 | Research chair contracted, or year 3 | Year 3 | 10,00,000 |
| 11 | Second BD Manager | 30 active partnerships | Year 3 | 13,00,000 |

## 2.1 The two gates that matter

Gate 1 — the Director gate. Moving the Programme Director from 0.5 to 1.0 costs ₹16 lakh a year. It is released only by ₹1 crore of contracted forward revenue, meaning signed engagements with dates, not pipeline. Tested monthly from month 10.

Gate 2 — the Curriculum gate. Moving the Head of Curriculum from retained to employed costs ₹14 lakh a year. It is released by 15 programmes a year or 12 certified bench trainers, whichever comes first. The bench measure usually triggers first, and should — a bench of twelve cannot be maintained by a retained consultant.

# 3. Year 1 operating budget

## 3.1 Revenue

| # | Line | Units | Revenue | Contribution |
| --- | --- | --- | --- | --- |
| 1 | Advisory retainer, comprehensive | 3 | 10,80,000 | 3,42,000 |
| 2 | Advisory retainer, standard | 3 | 5,40,000 | 1,56,000 |
| 3 | Coaching, international | 5 | 11,25,000 | 6,50,000 |
| 4 | Coaching, national | 3 | 3,30,000 | 1,47,000 |
| 5 | Faculty Development Programmes | 6 | 21,00,000 | 7,31,400 |
| 6 | Institutional workshops | 10 | 6,50,000 | 3,65,000 |
| 7 | POSH and grievance sessions | 3 | 2,70,000 | 1,35,000 |
| 8 | Curriculum licences | 2 | 2,50,000 | 2,20,000 |
|  | Total |  | 63,45,000 | 27,46,400 |
|  | Blended contribution margin |  |  | 43.3% |

## 3.2 Fixed and investment cost

| # | Line | Basis | Amount |
| --- | --- | --- | --- |
| People |  |  |  |
| 1 | Programme Director, 0.5 allocation | Existing executive | 12,00,000 |
| 2 | Manager — BD & Programmes | From month 1 | 12,00,000 |
| 3 | Head of Curriculum, retained 0.3 | From month 1 | 7,00,000 |
| 4 | Coordinator, 0.4 | From month 3 | 2,00,000 |
| 5 | Marketing Executive, 0.5 | From month 7 | 2,00,000 |
|  | People sub-total |  | 35,00,000 |
| Shared services |  |  |  |
| 6 | Finance 0.3, Legal 0.3, DPO 0.2 | Group allocation | 4,20,000 |
| Go-to-market |  |  |  |
| 7 | Travel and business development | 40 approaches, 20 meetings | 4,00,000 |
| 8 | Marketing, collateral, digital | Decks, website, print, video | 2,50,000 |
| 9 | Competition sponsorship and judging | 5 events per 01.6 s.7.1 | 3,50,000 |
| Investment |  |  |  |
| 10 | Trainer bench build | Per 07.11 s.7.1 | 4,02,000 |
| 11 | Curriculum production — printing, artwork, digital resource set | One-off | 1,80,000 |
| Overheads |  |  |  |
| 12 | Systems — CRM, registration, scoring, storage | Annual | 1,20,000 |
| 13 | Insurance — professional indemnity, public liability | Annual | 1,40,000 |
| 14 | Trade marks and legal set-up | One-off | 1,10,000 |
| 15 | Contingency at 5% |  | 3,00,000 |
|  | Total cost |  | 61,72,000 |

## 3.3 Result

|  | Amount |
| --- | --- |
| Contribution | 27,46,400 |
| Total cost | (61,72,000) |
| Year 1 result | (34,25,600) |
| Add back: trainer bench investment | 4,02,000 |
| Add back: curriculum production, one-off | 1,80,000 |
| Add back: trade marks and set-up, one-off | 1,10,000 |
| Underlying operating result | (27,33,600) |
| Add back: competition sponsorship, customer acquisition | 3,50,000 |
| Operating result before customer acquisition | (23,83,600) |

A note on presentation. The headline number is a ₹34.3 lakh loss. The Board should see all three lines. Roughly ₹7 lakh is one-off investment in assets that persist — a trainer bench, a curriculum and registered marks — and ₹3.5 lakh is customer acquisition that produces year 2 sponsorship and coaching revenue. Presenting only the headline understates what the year buys.

## 3.4 Reconciliation to 01.6

01.6 section 4.1 shows a ₹17.9 lakh loss against a ₹45.4 lakh cost base. This budget is more complete — it adds shared services, curriculum production, systems, insurance, trade marks and contingency, which 01.6 omitted. This document supersedes that table. The strategic conclusions in 01.6 are unaffected: the mix is right, the bench must be funded, and the Director gate is worth ₹16 lakh.

# 4. Cash profile

| Quarter | Revenue received | Cost paid | Net | Cumulative |
| --- | --- | --- | --- | --- |
| Q1 | 4,50,000 | 16,80,000 | (12,30,000) | (12,30,000) |
| Q2 | 12,80,000 | 17,20,000 | (4,40,000) | (16,70,000) |
| Q3 | 20,10,000 | 14,60,000 | 5,50,000 | (11,20,000) |
| Q4 | 26,05,000 | 13,12,000 | 12,93,000 | 1,73,000 |
| Year 1 | 63,45,000 | 61,72,000 |  |  |

Peak cash requirement: approximately ₹19 lakh, in month 7 to 8.

Q1 is the hardest quarter: costs are fully loaded, the bench investment falls here, and revenue has not started. Funding must be committed before month 1, not sought in month 6.

## 4.1 Working capital discipline

Rule

40% advance on every institution-paid programme, invoiced on confirmation of dates

Advisory retainers invoiced quarterly in advance

Coaching invoiced 50% on engagement

No new delivery to an institution with an undisputed invoice beyond 60 days

Trainer payment at 21 days — this one is not negotiable even in a tight quarter

# 5. Year 2 and 3 outline

|  | Year 2 | Year 3 |
| --- | --- | --- |
| Employed FTE | 6.6 | 9.6 |
| People cost | 58,00,000 | 82,00,000 |
| Other fixed and investment | 26,00,000 | 34,00,000 |
| Total cost | 84,00,000 | 1,16,00,000 |
| Revenue | 2,06,03,000 | 3,64,00,000 |
| Contribution at 45.5% / 46% | 93,74,000 | 1,67,44,000 |
| Competition outturn | (2,19,500) | 6,54,000 |
| Result | 7,54,500 | 57,98,000 |

[verify — re-base after two quarters of actual delivery. These are planning figures.]

# 6. Hiring process

| Stage | Detail |
| --- | --- |
| Approval | Trigger evidenced in writing; Programme Board approves the requisition |
| Description | From 12.1, unamended except for the deliverables section |
| Sourcing | Direct approach preferred; sector networks; Equator's own alumni and trainer bench from year 2 |
| Screening | Written exercise for every role — the writing standard in this programme is high and cannot be assessed by interview |
| Interview | Two stages; structured; scored; one stage includes a scenario on judgement or conflict |
| References | Two, taken before offer |
| Offer | Per the Delegation of Authority |
| Onboarding | 30-day plan; the full document set is required reading; policies signed |

## 6.1 The written exercise, by role

| Role | Exercise |
| --- | --- |
| Programme Director | One page: how you would sequence the first 90 days, and what you would refuse to do |
| Manager BD | Draft an approach letter to a named Dean, from a one-paragraph brief |
| Head of Curriculum | Design a 90-minute session on a stated skill, with the debrief plan |
| Manager Operations | Given a programme going wrong on the morning, what do you do in the first hour |
| Coordinator Internships | A student tells you something in confidence that you think must be escalated. Write what you say to them |
| Marketing | Rewrite a supplied paragraph that contains three prohibited claims |

The Coordinator exercise is the most predictive in the set. The role turns on knowing when confidentiality yields, and on being able to say so kindly.